## Jira Import — Full Backlog
DEXTER / MIDAS — Jira Import: Full Program Backlog (v8, 2026-03-31)
Issue ID | Issue Type | Epic Link | Epic Name | Wave | Team (Topology) | Summary | Priority | Status | Story Pts | Labels | Description (truncated)
▶ WAVE 0 — Assurance & Ops
CRON-1 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Assurance & Ops | Fix cron UTC offset: 45 5 → 10 45 (fires at 01:45 ET, not 05:45 ET) | High | OPEN | 1 | wave-0 | Current: 45 5 * * * UTC = 01:45 ET. Target: 10 45 * * 1-5 UTC = 05:45 ET EST. This means the ETL runs in the middle of the night on yesterday's data. Fix before next market day.
CRON-2 | Story | MIDAS-4 | Security | WAVE 0 | Assurance & Ops | Remove API keys from cron prompt body — move to env vars | Critical | OPEN | 2 | wave-0 | FINNHUB_KEY, FRED_API_KEY, SLACK_WEBHOOK are in plaintext in the cron prompt string. Anyone with cron config access sees all three credentials. Move to Azure VM environment variables or Key Vault. ETL
CRON-3 | Story | MIDAS-4 | Security | WAVE 0 | Assurance & Ops | Fix SLACK_WEBHOOK double-fire — remove from cron prompt body | High | OPEN | 1 | wave-0 | SLACK_WEBHOOK in both prompt body and delivery config. ETL already posts its own Slack alert at run end. Remove from prompt body to prevent duplicate messages on every run.
CRON-4 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Assurance & Ops | Add dexter_notebooklm_upload.py as cron step 3 (after ETL, before Phase 0) | High | OPEN | 1 | wave-0 | HEARTBEAT 05:55 step. Must run after ETL (which creates the files) and before Phase 0 (which reads them from NotebookLM). All source files must be in notebook before OpenClaw synthesises.
CRON-5 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Assurance & Ops | Add OpenClaw Phase 0-5 as cron step 6 | High | OPEN | 2 | wave-0 | Signal Aggregator through GMISR Reporter entirely absent from cron. Phase 0→0.5(conditional)→1→2→3→4→5 must be scheduled after NotebookLM upload completes.
CRON-6 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Assurance & Ops | Add DAILY_STATE.md update as cron step 7 (after Phase 5) | Medium | OPEN | 1 | wave-0 | Phase 5 output feeds DAILY_STATE.md carry-over. Currently not scheduled. Shadow journal section must be filled manually before re-opening NotebookLM.
CRON-7 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Assurance & Ops | Rename feedmd_config_03-01-2026.yml to date-agnostic name | Medium | OPEN | 1 | wave-0 | Hardcoded date in config filename. Will silently use a March 1st config indefinitely. Rename to feedmd_config.yml or derive name dynamically.
CRON-8 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Assurance & Ops | Restrict cron to weekdays (1-5) and confirm weekend intent | Medium | OPEN | 1 | wave-0 | Currently * * * = 7 days/week. Weekend ETL produces stale data. Recommend 1-5 unless Saturday/Sunday runs are intentional. Weekend data could confuse Monday Phase 1 regime read.
DOCS-AGENTS | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | AGENTS.md v1.1 — model, ETL spec, conflict logic, phase order | Medium | DONE | 2 | wave-0 | Main agent upgraded to gemini-3-flash-preview. ETL spec 1.2.0.0→1.7.5.6. FRA-OIS conflict logic corrected (CB Supremacy). EDGAR web_fetch scope corrected. TIER_AUDIT anchor + CONVICTION_CAP + phase se
DOCS-HEARTBEAT | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | HEARTBEAT.md v1.1 — 11 fixes | High | DONE | 2 | wave-0 | ETL run at 05:45. NotebookLM upload at 05:55. Phase 0 at 06:00. Phase 0.5 conditional slot. DOLLAR_DECOMP gate check. Phase 5 explicit. DEXTER_SENTINEL→MIDAS_SENTINEL log. 30m FRA-OIS polling removed
DOCS-MACRO | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | MACRO_TIERS v3.2 — ETL 1.7.5.6 sync | Medium | DONE | 2 | wave-0 | Tier -1.5 auctions_query promoted to primary (TA_WS=fallback). Tier 3 DTWEXBGS→DTWEXM fix + sanity gate. Full Dollar Decomposition 4-layer section added. Naming fixed.
DOCS-MANIFEST | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | MIDAS_SENTINEL_PROMPT_LIBRARY v2026.4 — 3 corrections | Medium | DONE | 2 | wave-0 | CONVICTION_CAP 0.4 schema added. DOLLAR_DECOMP + BALTIMORE_PSC in checklist. Daily source filenames corrected to ETL 1.7.5.x names. Phase 0 added to TIER_AUDIT integrity table.
DOCS-NAMING | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | Naming standardisation — Dexter ETL / Midas Sentinel | Medium | DONE | 1 | wave-0 | Dexter = ETL/data layer. Midas Sentinel = analysis/OpenClaw layer. 6 violations fixed across dexter_etl, MACRO_TIERS, REGIME_RULES, MIDAS_SENTINEL manifest. Zero violations remaining.
DOCS-NOTEBOOKLM | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | dexter_notebooklm_upload.py — automated daily upload | High | DONE | 2 | wave-0 | Uploads all ETL output files + foundation docs to NotebookLM in tier priority order. TIER_AUDIT first. dexter_notebooklm_upload.py using notebooklm-py (teng-lin). --dry-run flag. DEXTER_DATA_DIR + DEX
DOCS-OC-SOUL | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | OPENCLAW_SOUL 2026.3.22 — 6 logic fixes | High | DONE | 2 | wave-0 | Phase scope 1-5→0-5. 40bps Rubicon logic corrected (Regime A elevated, not Regime C). Canonical threshold source: SOUL §3 not SYNC_CONTRACT. DTCC→SEC FTD. Dollar Decomp + CONVICTION_CAP 0.4 + GatePass
DOCS-REGIME | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | REGIME_RULES v2.3 — Dollar Decomp wired into weighting | Medium | DONE | 1 | wave-0 | COMMODITY_REGIME + 4 other composites added to Tier 3 rows and ETL→Regime mapping table. ETL sync 1.7.5.6. Naming fixed.
DOCS-SOUL | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | SOUL v2.4 — §3.1 Dollar Decomp supplement | Medium | DONE | 1 | wave-0 | §3.1 Dollar Decomposition added with composite table. ETL filename reference updated. MACRO_TIERS v3.2 xref. Naming fixed.
ETL-1.7.5.5 | Story | MIDAS-1 | ETL Bug Fixes | WAVE 0 | Assurance & Ops | CFTC Layer 4 — partial 404 fix (Socrata SODA endpoint) | High | DONE | 1 | wave-0 | Replaced /api/detail/cot (404) with /resource/6dca-aqww.json Socrata SODA. OData→SoQL query syntax. Superseded by 1.7.5.6.
ETL-1.7.5.6 | Story | MIDAS-1 | ETL Bug Fixes | WAVE 0 | Assurance & Ops | CFTC Layer 4 — confirmed live endpoint /api/v3/ | High | DONE | 2 | wave-0 | Live endpoint confirmed: /api/v3/views/6dca-aqww/query.json with app_token. Default sort is ASC from 2000 — $order DESC mandatory. 2-source fallback chain. Layer 4 now live: net=-9,180 NEUTRAL. COMMOD
SYNC-1.3 | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | DEXTER_SYNC_CONTRACT v1.3 — CFTC endpoint + version pairing | Medium | DONE | 1 | wave-0 | Ticker registry updated with confirmed /api/v3/ endpoint, app_token, dataset ID, ascending-sort warning. Version pairing log rows for 1.7.5.1–1.7.5.6 added.
▶ WAVE 1 — Assurance & Ops
DL-1 | Story | MIDAS-5 | Dead-Letter Queue | WAVE 1 | Assurance & Ops | Define DeadLetterEntry dataclass and criticality map | Medium | DONE | 3 | wave-1 | Typed DeadLetterEntry: timestamp, module, source_name, url, error_type, error_detail, is_critical, retry_hint. Critical sources: FRED WALCL/SOFR, yfinance VIX. Non-critical: Treasury auctions.
DL-2a | Story | MIDAS-5 | Dead-Letter Queue | WAVE 1 | Assurance & Ops | Thread dead-letter through run_fred() and run_treasury() (M1/M2) | Medium | DONE | 2 | wave-1 | Dead_letters list wired into Modules 1 and 2. Bare except replaced with DeadLetterEntry append.
DL-2b | Story | MIDAS-5 | Dead-Letter Queue | WAVE 1 | Assurance & Ops | Thread dead-letter through run_market() and run_fed_and_dtcc() (M3/M5) | Medium | DONE | 2 | wave-1 | Dead_letters list wired into Modules 3 and 5.
DL-2c | Story | MIDAS-5 | Dead-Letter Queue | WAVE 1 | Assurance & Ops | Thread dead-letter through run_news() and run_calendars() (M7/M6) | Medium | OPEN | 2 | wave-1 | Two remaining function signatures need dead_letters parameter. run_news() has many feed sources that currently fail silently. run_calendars() Finnhub calls.
DL-3 | Story | MIDAS-5 | Dead-Letter Queue | WAVE 1 | Assurance & Ops | Write FAILED_{date}.json + DATA_FAILURES block in TIER_AUDIT | Medium | OPEN | 3 | wave-1 | After all modules complete: write FAILED_{run_date}.json. In build_tier_audit(): count critical failures, reduce CONVICTION_CAP by 0.2 per critical failure (floor 0.2), append DATA_FAILURES section.
OO-1 | Story | MIDAS-6 | Offline Observer | WAVE 1 | Assurance & Ops | Define OBSERVATION_RULES dict per module | Low | DONE | 2 | wave-1 | Expected minimums: FRED >= 400 chars + NET LIQUIDITY string; Auctions >= 10 records; Market CSV >= 15 rows; EDGAR >= 500 chars + PRIORITY 1; News >= 20000 chars + 8 sources; Calendars >= 100 chars.
OO-2 | Story | MIDAS-6 | Offline Observer | WAVE 1 | Assurance & Ops | Implement run_offline_observer() as Module 9.5 | Medium | OPEN | 5 | wave-1 | Runs after all modules, before build_tier_audit(). Reads each output file, applies OBSERVATION_RULES, builds observations dict with actual vs expected, pass/fail, degradation level. Cross-references d
OO-3 | Story | MIDAS-6 | Offline Observer | WAVE 1 | Assurance & Ops | Inject observation results into TIER_AUDIT and completion banner | Low | OPEN | 3 | wave-1 | Pass observations to build_tier_audit(). Add DATA_QUALITY_REPORT section. CORPUS_QUALITY = (passing/total) × 100. Print in banner alongside CONVICTION_CAP.
▶ WAVE 2 — Assurance & Ops
AW-1 | Story | MIDAS-7 | AWAP Pattern | WAVE 2 | Assurance & Ops | Create staging/ directory structure and write_staged() helper | Medium | OPEN | 3 | wave-2 | Staging subdirectory in dexter_data/YYYYMMDD/. write_staged() writes to staging first; promote() copies to final. Final output files only exist if they passed audit. NotebookLM uploads from root, neve
AW-2 | Story | MIDAS-7 | AWAP Pattern | WAVE 2 | Assurance & Ops | Implement pre-write input audit (Audit step 1) | High | OPEN | 8 | wave-2 | audit_input(module, data, rules) → (passed, errors). Per module: FRED all 9 series non-None; market VIX/DGS10/one equity; EDGAR P1 or P2 hit; news 3+ feeds. Fail: write DEGRADED to staging, append dea
AW-3 | Story | MIDAS-7 | AWAP Pattern | WAVE 2 | Assurance & Ops | Implement post-write output audit (Audit step 2) | High | OPEN | 5 | wave-2 | audit_output(staged_path, rules). FRED_SUMMARY: all 9 labels; COMMODITIES: WTI+Brent non-zero; TIER_AUDIT: all required sections. Pass → promote(). Fail → AUDIT_FAILED_{module}_{date}.txt.
AW-4 | Story | MIDAS-7 | AWAP Pattern | WAVE 2 | Assurance & Ops | Implement three audit failure strategies (Fail/Dispatch/Ignore) | Medium | OPEN | 5 | wave-2 | Per-module AUDIT_FAILURE_STRATEGY: Fail (FRED), Dispatch to dead-letter (Treasury/market), Ignore+DEGRADED (news). TIER_AUDIT reflects which strategy fired.
SC-1 | Story | MIDAS-8 | Schema Compat | WAVE 2 | Assurance & Ops | Define expected schemas for all external API responses | Medium | OPEN | 3 | wave-2 | SCHEMAS dict in schema_registry.py. Treasury auctions_query required fields. FRED observations list. EDGAR _source with file_date. yfinance DataFrame with Close. Mark required/optional/deprecated.
SC-2 | Story | MIDAS-8 | Schema Compat | WAVE 2 | Assurance & Ops | Implement validate_schema() and inject into fetch steps | High | OPEN | 5 | wave-2 | validate_schema(data, schema) → (compatible, drift_report). Three outcomes: compatible; forward-compatible (new optionals, log); backward-incompatible (required missing, → SCHEMA_DRIFT dead_letter). I
SC-3 | Story | MIDAS-8 | Schema Compat | WAVE 2 | Assurance & Ops | Write SCHEMA_DRIFT report and auto-update optional field registry | Low | OPEN | 3 | wave-2 | SCHEMA_DRIFT_{date}.txt when new optionals appear. Auto-learn: new field 3 runs in a row → add to optional list with comment. Backward-incompatible → CRITICAL flag, halt module.
▶ WAVE 3 — Data Foundry
ID-1 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | Define idempotency granularity and document the contract | Low | DONE | 1 | wave-3 | run_date (YYYYMMDD) is the idempotency partition key. dexter_data/YYYYMMDD/ is one atomic unit. Two runs for same date produce identical output (same API responses).
ID-2 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | Fix FRED_SUMMARY append bug — most urgent idempotency violation | High | DONE | 2 | wave-3 | Treasury XML block moved before write_file() in run_fred(). Built as tsy_block='', written once as summary+tsy_block. No read_text() anywhere. Confirmed fixed in 1.7.5.2.
ID-3 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | Implement atomic write via stage-then-rename (write_atomic) | High | OPEN | 5 | wave-3 | write_atomic(path, content): write to path.with_suffix('.tmp'), then os.replace(tmp→final). Atomic on POSIX. Add startup cleanup of *.tmp orphans. Replaces write_file() everywhere.
ID-4 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | Add run MANIFEST.json with schema version and ETL script hash | Medium | OPEN | 5 | wave-3 | MANIFEST.json in dexter_data/YYYYMMDD/: run_date, etl_version (hash), schema_version, modules_completed, run_start/end. On re-run: skip completed modules unless --force-rerun.
ID-5 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | Make EDGAR incremental with delta-column state file (edgar_state.json) | Medium | OPEN | 5 | wave-3 | State file with last_successful_fetch_dt. since = max(last_fetch, today-14d). After successful write update state. 14-day backfill window. Eliminates ghost-filing problem.
ID-6 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | --force-rerun flag and idempotency test procedure | Medium | OPEN | 3 | wave-3 | CLI flag: delete manifest, clear staging, re-run all. Test: run twice for same date, diff output — byte-identical except TIER_AUDIT timestamp.
▶ WAVE 4 — Sentinel Alpha
SCRAP-1 | Story | MIDAS-10 | Scrapling | WAVE 4 | Sentinel Alpha | Refactor scrapling_news.py — Category A sources only | High | OPEN | 3 | wave-4 | Remove all 10 overlap sources (Reuters/FT/WSJ/CNBC/MarketWatch/BIS/Fed/FRED/SEC/Google — ETL already covers these). Keep: BoJ, PBOC, BoE, BCB, RBI, SAMA, Caixin, Risk.net, Trading Economics, Al Jazeer
SCRAP-2 | Story | MIDAS-10 | Scrapling | WAVE 4 | Sentinel Alpha | Write merge_scrapling_into_corpus.py — append §SCRAPLING_SUPPLEMENT to NEWS_CORPUS | High | OPEN | 3 | wave-4 | Reads scraping output directory, reads existing NEWS_CORPUS_{date}.txt, appends §SCRAPLING_SUPPLEMENT section with tier-tagged content. Must run after ETL (NEWS_CORPUS must exist first) and before Not
SCRAP-3 | Story | MIDAS-10 | Scrapling | WAVE 4 | Sentinel Alpha | Document scrapling data lineage in SYNC_CONTRACT v1.4 | Medium | OPEN | 1 | wave-4 | Add scrapling_news.py to source registry. Map Category A sources to MACRO_TIERS tiers: BoJ/PBOC/BoE → Tier -1, Caixin → Tier 2/3, Risk.net → Tier -1/4. Document cron step order dependency.
SCRAP-4 | Story | MIDAS-10 | Scrapling | WAVE 4 | Sentinel Alpha | Wire scrapling Category A sources into MACRO_TIERS tier routing | Medium | OPEN | 2 | wave-4 | Add BoJ/PBOC/BoE/BCB/RBI to MACRO_TIERS Tier -1 source list. Add Caixin/Brazil Journal to Tier 2/3 HDS routing. Add Risk.net to Tier -1 specialist sources. Update MACRO_TIERS v3.3.
▶ WAVE 5 — Sentinel Alpha
DELTA-1 | Story | MIDAS-12 | Model Delta | WAVE 5 | Sentinel Alpha | Add Claude (Anthropic API) as Lineage B agent in AGENTS.md | Medium | OPEN | 3 | wave-5 | Add second researcher agent using Claude Sonnet via Anthropic API. Lineage A = Gemini flash-preview, Lineage B = Claude Sonnet. Both run Phase 3 (Fundamental Agent) independently on same corpus.
DELTA-2 | Story | MIDAS-12 | Model Delta | WAVE 5 | Sentinel Alpha | Write Phase 3.5 delta synthesiser prompt | Medium | OPEN | 3 | wave-5 | New phase between Phase 3 and Phase 4. Takes both NARRATIVE_ALPHA contracts (Lineage A + B). Identifies agreements (high confidence), disagreements (flag for human review), and synthesises into a sing
DELTA-3 | Story | MIDAS-12 | Model Delta | WAVE 5 | Sentinel Alpha | Add Model Delta block (Block 4) to Phase 5 GMISR schema | Medium | OPEN | 2 | wave-5 | Block 4 in GMISR: what did Lineage A say, what did Lineage B say, where did they diverge, what was the synthesis decision. Maps to v1.0 Block 4.
DELTA-4 | Story | MIDAS-12 | Model Delta | WAVE 5 | Sentinel Alpha | Define sizing rule from lineage delta | Low | OPEN | 2 | wave-5 | When Lineage A and B disagree on direction: use cautionary lineage for position sizing (per v1.0 logic: Claude divergence for pair selection, ChatGPT cautionary sizing). Encode in Phase 4 SENTENCE_DIR
GMISR-1 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add GICS codes to SENTENCE_DIRECTIVE setups (Phase 4 prompt) | High | OPEN | 2 | wave-5 | Every driver and active setup must carry full GICS code (e.g. 45103010). Phase 4 prompt addition. No ETL change required.
GMISR-2 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add qualitative invalidation condition per driver | High | OPEN | 2 | wave-5 | Each setup in SENTENCE_DIRECTIVE must include: INVALIDATION: [specific condition that cancels the thesis]. e.g. 'US-Iran ceasefire' or 'CEO retracts exit'. Phase 4 prompt addition.
GMISR-3 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add Catalyst Map 24h/48h/72h as Block 10 to Phase 5 GMISR schema | High | OPEN | 2 | wave-5 | Structured forward-looking catalyst timeline: what to watch for in next 24h, 48h, 72h. Phase 5 prompt schema addition. Corresponds to v1.0 Block 10.
GMISR-4 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add structured pair trade output to Phase 5 | High | OPEN | 2 | wave-5 | Phase 5 GMISR Strategy Matrix block: Long [TICKER] ([GICS]) / Short [TICKER] ([GICS]) with GICS sector logic. Replaces individual setup list. Phase 5 prompt schema addition.
GMISR-5 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add per-claim source citation (Block 11 Data Lineage) to Phase 5 | Medium | OPEN | 2 | wave-5 | Phase 5 GMISR Data Lineage block: cite source per major claim. Financial tables, geopolitical, macro/credit sources named. Phase 5 prompt addition.
GMISR-6 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add NDI (Narrative Divergence Index) to Phase 3 NARRATIVE_ALPHA output | Medium | OPEN | 2 | wave-5 | Count distinct narrative clusters in NEWS_CORPUS. Score 0-1. Add to NARRATIVE_ALPHA contract as NDI field. Phase 3 prompt addition.
GMISR-7 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add Narrative Velocity / NLLI scoring to Phase 3 | Medium | OPEN | 3 | wave-5 | Score velocity of emerging vs established narrative clusters. New cluster gaining saturation = positive NLLI. Add NLLI to NARRATIVE_ALPHA contract.
IQ-5 | Story | MIDAS-14 | Advanced Signals | WAVE 5 | Sentinel Alpha | COT/CFTC positioning (Module 6b Layer 4) — LIVE | Medium | DONE | 2 | wave-5 | CFTC non-commercial net long on USD Index (098662) via /api/v3/. Confirmed working 2026-03-22. net=-9,180 = NEUTRAL. Composite unaffected by positioning at this level.
SCORE-1 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement HDS auto-scoring in run_news() | Medium | OPEN | 5 | wave-5 | Compute Headline Density Score per tier: count of matching headlines per tier_keywords group / total items. Write HDS per tier to NEWS_CORPUS header section. Top 3 themes by count = blob detection.
SCORE-2 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement VPI (Volatility Pricing Index) in build_tier_audit() | Medium | OPEN | 3 | wave-5 | VPI = VIX_spot / (5-day realized vol proxy). VIX > realized → VIX lagging = VPI > 1 (underpriced stress). Requires 5-day VIX history from RUN_HISTORY.log. Add to TIER_AUDIT.
SCORE-3 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement LFI (Liquidity Friction Index) in build_tier_audit() | Medium | OPEN | 5 | wave-5 | LFI = composite of: FRA-OIS normalised (0-1 over 0-60bps range) + BDC price discount to NAV proxy + EDGAR 8-K withdrawal/redemption count. Write to TIER_AUDIT.
SCORE-4 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement NLLI (Narrative Lag-Lead Indicator) in run_news() | Medium | OPEN | 5 | wave-5 | Compare current run's tier headline counts to prior 5-run rolling average. Rising count in tier = positive NLLI for that tier. Write NLLI vector to NEWS_CORPUS header.
SCORE-5 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement CCS (Cross-Correlation Score) in run_market() | Low | OPEN | 5 | wave-5 | CCS = correlation between ratio-pair movements (TQQQ/SQQQ, Gold/NASDAQ etc) vs broad index. Low CCS = idiosyncratic alpha opportunity. Requires 5-day price history.
SCORE-6 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement CXOD (Cross-Asset Order Delta) in run_market() | Low | OPEN | 3 | wave-5 | CXOD = signed flow divergence: (USO 1d return) - (QQQ 1d return). Positive = energy bid, equities sold. Negative = risk-on. Write to COMMODITIES/EQUITIES files.
SCORE-7 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement PSI (Policy Sensitivity Index) in build_tier_audit() | Low | OPEN | 5 | wave-5 | PSI = composite of: GDP revision magnitude + FRA-OIS level + high-impact events within 5 days + earnings guidance revision count. Higher PSI = higher policy error risk.
T4-10 | Story | MIDAS-14 | Advanced Signals | WAVE 5 | Sentinel Alpha | RATIO_SIGNALS named section in TIER_AUDIT — schema 2.0.0.0 | High | OPEN | 8 | wave-5 | Major schema change: add dedicated RATIO_SIGNALS section listing all SOUL §3 ratio pair statuses in a consistent format. Requires build_tier_audit() rewrite and version bump.
T4-8 | Story | MIDAS-14 | Advanced Signals | WAVE 5 | Sentinel Alpha | Gold/NASDAQ absolute >0.30 flag in TIER_AUDIT | Medium | OPEN | 2 | wave-5 | MA deviation exists (gn_ma_pct). Absolute ratio flag (gn_ratio > 300 at ×1000 scale) is missing from TIER_AUDIT. Add as separate row in TIER_5 block.
▶ WAVE 6 — Quant Lab
OB-1 | Story |  | Observability | WAVE 6 | Assurance & Ops | SLA monitoring — per-module timing + elapsed alert (SLA Misses Detector) | High | OPEN | 3 | topology,assurance-&-ops | Add timing instrumentation to each ETL module: record start_time, end_time, elapsed_s. Write to RUN_HISTORY.log alongside existing completion status. Alert thresholds: total run > 10 min = WARNING Sla
OB-2 | Story |  | Observability | WAVE 6 | Assurance & Ops | Skew Detector — BTC (bid-to-cover) count vs 4-week rolling average | High | OPEN | 2 | topology,assurance-&-ops | Compute rolling_avg_btc = mean of last 20 auction BTC values per security type. Flag: if current BTC deviates > 15% from rolling_avg = AUCTION_SKEW alert in TIER_AUDIT. Distinguishes one-off weak auct
OB-3 | Story |  | Observability | WAVE 6 | Assurance & Ops | Filter Interceptor — NEWS_CORPUS UNCLASSIFIED rate per feed | High | OPEN | 2 | topology,assurance-&-ops | In run_news(): compute pct_unclassified per RSS feed source. If any feed > 40% UNCLASSIFIED consistently (3 runs): flag feed for quality review. Write per-feed UNCLASSIFIED% to NEWS_CORPUS header alon
OB-4 | Story |  | Observability | WAVE 6 | Assurance & Ops | Data retention policy — TTL for raw ETL outputs + cleanup script | High | OPEN | 2 | topology,assurance-&-ops | Raw ETL text files in dexter_data/YYYYMMDD/: 30-day TTL. TIER_AUDIT files: indefinite retention (source of truth for shadow journal). GMISR_METRICS Parquet: indefinite retention (ML training data). Wr
OB-5 | Story |  | Observability | WAVE 6 | Assurance & Ops | Fine-grained lineage SOURCE_MAP — shared scope with IQ-7 | High | OPEN | 1 | topology,assurance-&-ops | Shared implementation with IQ-7 (SOURCE_MAP in TIER_AUDIT). OB-5 extends to the Parquet/Gold layer: each Parquet row includes source_hash column linking to the specific ETL run that produced it. Fine-
P1-1 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Add write_parquet_snapshot() to ETL main() | High | OPEN | 3 | topology,quant-lab | After build_tier_audit() completes, write one Parquet row to dexter_data/parquet/gmisr_metrics/ partitioned by run_date. 28 typed columns: all TIER_AUDIT scalars + scored metrics (HDS/VPI/LFI/NLLI/PSI
P1-2 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Define and lock GMISR_METRICS Parquet schema v1.0 | High | OPEN | 2 | topology,quant-lab | Create schema_registry.py entry for gmisr_metrics. 28 typed columns. Scored metric columns NULLABLE until SCORE-1/7 Wave 5 work lands. Schema version in MANIFEST.json. Breaking changes require migrati
P1-3 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Add phase1_agreement and actual_spx_5d ML label columns | High | OPEN | 3 | topology,quant-lab | phase1_agreement BOOL: written retrospectively from DAILY_STATE.md shadow journal field after Phase 10. actual_spx_5d FLOAT: forward-filled weekly cron — SPX return for runs where 5 trading days elaps
P1-4 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Write backfill_parquet.py — populate history from existing run archives | High | OPEN | 5 | topology,quant-lab | One-time script: reads RUN_HISTORY.log to enumerate past run dates, parses each dexter_data/YYYYMMDD/ TIER_AUDIT + FRED_SUMMARY + DOLLAR_DECOMP into structured dicts, writes Parquet rows for all histo
P2-1 | Story |  | Parquet snapshot layer | WAVE 6 | Sentinel Alpha | Set up DuckDB + Evidence.dev local dashboard | High | OPEN | 3 | topology,sentinel-alpha | pip install duckdb. Write dexter_analytics.py: connects to gmisr_metrics Parquet, exposes 5 standard queries (regime trend 90d, metric heatmap, conviction history, NLLI velocity chart, phase1_agreemen
P2-2 | Story |  | Parquet snapshot layer | WAVE 6 | Sentinel Alpha | Build 30/60/90-day regime and metrics dashboard | High | OPEN | 3 | topology,sentinel-alpha | Dashboard pages: (1) Regime timeline bar chart with conviction_cap overlay. (2) Scored metrics heatmap HDS/VPI/LFI/NLLI/PSI colour-coded by week. (3) Dollar decomp history COMMODITY_REGIME vs TRUE_RIS
P3-1 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Implement Feast feature store — point-in-time correct training sets | High | OPEN | 5 | topology,quant-lab | pip install feast. Define FeatureView over gmisr_metrics Parquet. Entity = run_date. Features = all scored metrics + tier fields. Materialise to local SQLite online store. Key function: get_historical
P4-1 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Build regime classifier v1.0 — HMM on scored metrics | High | OPEN | 8 | topology,quant-lab | Requires >= 30 labelled run_dates (Kelly activation gate). Features: [HDS, VPI, LFI, VX_ratio, FRA-OIS, net_liq_roc, NLLI]. Label: regime A/B/C. Model: Hidden Markov Model (hmmlearn). Regime = hidden
P4-2 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Build SENTENCE_DIRECTIVE outcome tracker — P&L attribution log | High | OPEN | 5 | topology,quant-lab | For each SENTENCE_DIRECTIVE conviction >= 0.40: record entry trigger, stop, target, actual_exit, outcome (win/loss/stopped/expired). Write to trade_log.parquet partitioned by run_date. Phase 10 audito
P4-3 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Kelly fraction activation and SOUL.md v3.0 update | High | OPEN | 2 | topology,quant-lab | When trade_log >= 30 closed: compute win_rate and avg_win/loss_ratio. Kelly = win_rate - (1-win_rate)/ratio. Phase 10 produces Kelly note for SOUL.md. Fixed-fractional (1%) active until this gate. Tra
▶ WAVE 7 — Data Foundry
ARCH-1 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Provision Databricks workspace and Unity Catalog — midas.bronze/silver/gold namespaces | High | OPEN | 3 | topology,sentinel-alpha | Create Databricks workspace (Azure/AWS). Enable Unity Catalog. Create three-level namespace: catalog=midas, schemas=bronze/silver/gold. Grant Dexter ETL service principal WRITE on bronze, READ on silv
ARCH-2 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Define canonical entity resolution schema — ticker normalisation map | High | OPEN | 3 | topology,sentinel-alpha | Current state: GC=F (yfinance) vs GOLD (equities txt) vs COM_GOLD (proposed canonical). Build ENTITY_MAP table in Unity Catalog: source_id, source_system, canonical_id, asset_class. Examples: GC=F → C
ARCH-3 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Define temporal alignment standard — ISO-8601 UTC across all layers | High | OPEN | 2 | topology,sentinel-alpha | Current state: TIER_AUDIT uses ET timestamp, SEC_FTD uses YYYY-MM-DD date only, News corpus uses RFC-822 (Fri, 20 Mar 2026), FRED uses YYYY-MM-DD. Silver standard: all timestamps converted to ingest_t
BRNZ-1 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Register ETL flat-file outputs as Delta Lake Bronze tables in Unity Catalog | High | OPEN | 5 | topology,sentinel-alpha | Current Wave 6 P1-1 writes Parquet locally. Extend: also COPY INTO midas.bronze.{table} after each ETL run. One Bronze table per ETL output file type: bronze.fred_summary, bronze.market_data, bronze.t
BRNZ-2 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Add _rescued_data column handling for schema mismatches at Bronze ingest | High | OPEN | 3 | topology,sentinel-alpha | DLT auto-routes schema-mismatched fields to _rescued_data column rather than failing the pipeline. Implement: for each Bronze table, define expected schema. Mismatched rows land in _rescued_data as JS
BRNZ-3 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Implement calculation hash (Gate 4) on Bronze model outputs | High | OPEN | 3 | topology,sentinel-alpha | For TIER_AUDIT and DOLLAR_DECOMP outputs: compute SHA-256 hash of the decision fields (regime_label, conviction_cap, dollar_composite) at Bronze write time. Store hash in bronze.tier_audit.output_hash
GOLD-1 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Build mkt_regime_final Gold materialized view — REGIME_RULES.md as code | High | OPEN | 5 | topology,sentinel-alpha | Materialized view consuming silver.refined_market_prices + silver.sovereign_stress_monitor. Implements REGIME_RULES.md logic as SQL: Regime A: net_liq_roc < 0 AND fra_ois_bps BETWEEN 15 AND 40. Regime
GOLD-2 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Build risk_sentinel_status Gold materialized view — SOUL.md §3/§4 as code | High | OPEN | 5 | topology,sentinel-alpha | Materialised view computing CONVICTION_CAP and RISK_SENTINEL_TRIGGER from Silver data. CONVICTION_CAP logic: 1.0 (clean) → 0.5 (stale WALCL/SOFR) → 0.4 (vx_ratio 0.93-1.05) → 0.0 (halt). RISK_SENTINEL
GOLD-3 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Build liquidity_gate Gold materialized view — MACRO_TIERS §Tier -2 as code | High | OPEN | 3 | topology,sentinel-alpha | Materialised view: net_liq_b = WALCL - TGA - RRP (from silver.sovereign_stress_monitor). is_blocked = CASE WHEN net_liq_roc_b < 0 THEN TRUE ELSE FALSE END. gate_status = OPEN/RESTRICTED/CLOSED per Pha
GOLD-4 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Build backtest_integrity Gold table — DAILY_STATE.md shadow journal as first-class asset | High | OPEN | 3 | topology,sentinel-alpha | Append-only table consuming DAILY_STATE.md PHASE1_AGREEMENT field after each Phase 10 Sunday run. Schema: run_date, regime_label, phase1_agreement BOOL, phase1_delta TEXT, regime_dist_a FLOAT, regime_
GOLD-5 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Build sync_audit Gold table — DEXTER_SYNC_CONTRACT.md compliance as code | High | OPEN | 2 | topology,sentinel-alpha | Daily compliance check: verify ETL TRIGGERS dict values match SOUL §3 canonical thresholds. If any threshold drifts (e.g. fra_ois_watch_bps changes in code but not in SOUL §3): write SYNC_VIOLATION ro
MCP-1 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Wire Claude MCP Databricks connector to Gold tables — read-only service principal | High | OPEN | 3 | topology,sentinel-alpha | Databricks MCP server already in AGENTS.md connected list (dbc-0df8fb6d-4908.cloud.databricks.com). Configure: Claude reads midas.gold.* tables via MCP SQL queries. Claude does NOT calculate regime —
MCP-2 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Add Gold table query examples to Phase 0 and Phase 2 prompts in manifest | High | OPEN | 2 | topology,sentinel-alpha | Update MIDAS_SENTINEL_PROMPT_LIBRARY v2026.5: Phase 0 (Signal Aggregator): if Databricks MCP available, query midas.gold.risk_sentinel_status for run_date before reading TIER_AUDIT text. Gold table ta
SILV-1 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Build Silver DLT pipeline — refined_market_prices streaming table | High | OPEN | 5 | topology,sentinel-alpha | DLT streaming table consuming bronze.market_data + bronze.fred_summary + bronze.polymarket_signals. Gate 1 (Schema): enforce price DOUBLE, timestamp DATE, ticker STRING NOT NULL. Gate 2 (Quality): EXP
SILV-2 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Build Silver DLT pipeline — sovereign_stress_monitor streaming table | High | OPEN | 5 | topology,sentinel-alpha | Consuming bronze.dollar_decomp + bronze.treasury_auctions + bronze.econ_calendar. Gate 1: enforce us_de_spread DOUBLE, auction_btc DOUBLE, event_time TIMESTAMP. Gate 2: EXPECT (us_de_spread IS NOT NUL
SILV-3 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Build Silver DLT pipeline — settlement_risk_indices streaming table | High | OPEN | 3 | topology,sentinel-alpha | Consuming bronze.sec_ftd + bronze.edgar_filings. Gate 1: enforce symbol STRING, quantity_fails INTEGER, settlement_date DATE. Gate 2: EXPECT (price > 0 OR price IS NULL) ON VIOLATION QUARANTINE (SEC_F
SILV-4 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Implement Great Expectations suite — 7 named expectations against ETL file types | High | OPEN | 8 | topology,sentinel-alpha | Deploy GX (pip install great-expectations) as validation layer between Bronze and Silver. Expectation Suite: dexter_midas_silver_suite. Seven named expectations from document: (1) price_positive: expe
SYNC-4 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Update SYNC_CONTRACT v1.5 — Medallion layer mapping and temporal alignment standard | High | OPEN | 2 | topology,sentinel-alpha | Add Medallion section: Bronze: raw ETL output files registered in Unity Catalog. Silver: three refined tables with DLT pipelines and GX expectations. Gold: four decision tables as materialized views —
SYNC-5 | Story |  | Medallion Architecture | WAVE 7 | Sentinel Alpha | Annotate existing Wave 2/3/6 items with Medallion layer equivalence notes | High | OPEN | 1 | topology,sentinel-alpha | Add annotation to WBS descriptions for: AW-1/2/3/4 → 'local equivalent of Bronze→Silver Gate 1/2/3 logic.' SC-1/2/3 → 'local equivalent of Unity Catalog schema enforcement.' ID-3 → 'local equivalent o
▶ GOVERNANCE — Assurance & Ops
GOV-1 | Story | MIDAS-134 | Governance | GOVERNANCE | Assurance & Ops | Maintain DEXTER_SYNC_CONTRACT.md — canonical threshold + ticker registry | MED | ONGOING | 1 | governance | SYNC_CONTRACT is the single source of truth for all ETL thresholds and ticker IDs. Process: any change to ETL TRIGGERS dict requires simultaneous SYNC_CONTRACT update. Never update SOUL.md/MACRO_TIERS
GOV-2 | Story | MIDAS-134 | Governance | GOVERNANCE | Assurance & Ops | Foundation file versioning — SOUL/MACRO_TIERS/REGIME_RULES in sync with ETL | MED | ONGOING | 1 | governance | Version pairing rule: ETL MAJOR bump (x.0.0.0) requires all three foundation files updated. Current pairings: ETL 1.7.5.6 ↔ SOUL v2.4 / MACRO_TIERS v3.2 / REGIME_RULES v2.3. ETL 2.0.0.0 (Wave 4) requi
GOV-3 | Story | MIDAS-134 | Governance | GOVERNANCE | Assurance & Ops | NotebookLM corpus reload on MAJOR ETL version bumps | HIGH | ONGOING | 1 | governance | TIER_AUDIT schema change (MAJOR bump) = Phase 0 prompt may break. Protocol: on every MAJOR bump, perform full NotebookLM source replacement before running Phase 0 for the first time. Test: run Phase 0
GOV-4 | Story | MIDAS-134 | Governance | GOVERNANCE | Assurance & Ops | Sync workflow enforcement — ETL TRIGGERS = canonical, foundation files = English | MED | ONGOING | 1 | governance | Direction of truth: ETL TRIGGERS dict defines the threshold numbers. Foundation files (SOUL/MACRO_TIERS) describe those numbers in English. Never reverse: do not change SOUL.md and then update ETL to
Total Stories: 104

## Jira Automation Rules
DEXTER / MIDAS — Jira Automation Rules (Team Topologies + PgMP Governance)
Rule # | Rule Name | Trigger Condition | Condition Detail | Action | Action Detail | Priority
── | TEAM ROUTING RULES
R-01 | Route to Sentinel Alpha | Epic Link IN list | SCRAPLING, GMISR_V2.0, SCORED_METRICS, ADVANCED_SIGNALS, MODEL_DELTA, POLYMARKET_LAYER, ECON_CALENDAR, EDGAR_V2.0 | Set 'Team' field | Sentinel Alpha | HIGH
R-02 | Route to Data Foundry | Epic Link IN list | IDEMPOTENCY, INFRASTRUCTURE, MEDALLION_ARCHITECTURE, BRONZE_LAYER, SILVER_LAYER, GOLD_LAYER, CLAUDE_MCP_INTEGRATION | Set 'Team' field | Data Foundry | HIGH
R-03 | Route to Assurance & Ops | Epic Link IN list | ETL_BUG_FIXES, DOCS, SECURITY, DEAD-LETTER_QUEUE, OFFLINE_OBSERVER, AWAP_PATTERN, SCHEMA_COMPAT, OBSERVABILITY, GOVERNANCE | Set 'Team' field | Assurance & Ops | HIGH
R-04 | Route to Quant Lab | Epic Link IN list | PARQUET_SNAPSHOT_LAYER, DUCKDB_ANALYTICS_LAYER, FEATURE_STORE, ML_REGIME_CLASSIFIER, TRACK_B_SHADOW | Set 'Team' field | Quant Lab | HIGH
── | GOVERNANCE & DRIFT RULES
R-05 | Calculation Drift Guard | Issue Created OR In-Progress | Epic Link = GOLD_LAYER OR summary contains 'metric' OR summary contains 'regime' | Edit Issue Description | APPEND: ⚠️ PRE-REQ: All metric outputs from this task must include model_name suffix (e.g. _CLAUDE_SONNET_4_6) to prevent calculation drift per 2026-02-25 audit protocol. | CRITICAL
R-06 | Agent-First Tag | Issue Created | Summary contains 'OpenClaw' OR summary contains 'Claude MCP' OR summary contains 'agentic' | Add Label + Set Priority | Add label: agent-integrated. Set priority: High. | HIGH
R-07 | Medallion Integrity Sub-task | Issue Transitioned → Done | Component = Databricks-Platform OR Databricks-SQL | Create Sub-task in Assurance & Ops | Create: 'Validate Schema Drift in Unity Catalog for [parent issue]'. Assign to Assurance & Ops. Priority: High. | HIGH
R-08 | GOV-2 Foundation File Sync | Issue Transitioned → Done | ID contains 'ETL' AND summary contains 'MAJOR' OR version bump 2.x.0.0 tag | Create sub-tasks | Create 3 governance sub-tasks: (1) Update SOUL.md version (2) Update MACRO_TIERS version (3) Update REGIME_RULES version. Link all to MIDAS-134 (Governance epic). | CRITICAL
── | PHASE GATE RULES
R-09 | Kelly Gate Circuit Breaker | Issue Transitioned → Done | ID = P4-1 (HMM Classifier) OR ID = P4-3 (Kelly activation) | Send Slack Alert | Post to #dexter-alerts: '⚠️ HUMAN CHECK REQUIRED: ML Model P4-1/P4-3 complete. Verify 30-trade shadow journal PHASE1_AGREEMENT >= 90% before promoting HMM weights to SOUL.md v3.0' | CRITICAL
R-10 | ARCH-1 Gate Enforcement | Epic Transitioned → In Progress | Epic Link IN (BRONZE_LAYER, SILVER_LAYER, GOLD_LAYER, CLAUDE_MCP_INTEGRATION) | Check Blocker | Block all Wave 7 stories with blocker link to ARCH-1 (Provision Databricks workspace). Do not allow In Progress unless ARCH-1 = DONE. | CRITICAL
R-11 | Wave Gate: Corpus before ML | Issue Created | Epic Link IN (PARQUET_SNAPSHOT_LAYER, ML_REGIME_CLASSIFIER) | Add Blocker Link | Auto-link as BLOCKED BY: AW-2 (AWAP audit), SC-2 (schema validation), ID-3 (atomic write). These Wave 2/3 items must be DONE. | HIGH
R-12 | GX Gate Enforcement | Issue Transitioned → In Progress | Epic Link = GOLD_LAYER | Check Blocker | Block Gold layer work with blocker to SILV-4 (Great Expectations suite). Gold should not be published until Silver GX suite passes at ≥99.5%. | HIGH
── | OBSERVABILITY RULES
R-13 | SLA Miss Alert | Scheduled daily | OB-1 (SLA Monitor) active: ETL run total > 20 minutes | Send Slack Alert | Post to #dexter-alerts: CRITICAL SLA MISS — ETL runtime exceeded 20min threshold. Tag Assurance & Ops lead. | CRITICAL
R-14 | Unclassified News Alert | Scheduled (weekly audit) | OB-3 (Filter Interceptor): any feed > 40% UNCLASSIFIED for 3 consecutive runs | Create Jira Issue | Auto-create Issue: 'FEED QUALITY DEGRADED: [feed name] at [X]% unclassified'. Assign to Assurance & Ops, Priority: Medium. | MEDIUM
R-15 | Complex Subsystem Alert | Issue Created OR Estimated | Team = Quant Lab AND Story Points > 5 | Add Comment | Auto-comment: '🧠 HIGH-COMPLEXITY ML TASK: Ensure OpenClaw has been used to draft initial pseudocode before manual dev begins. Consider pair-programming with Sentinel Alpha for signal validation.' | MEDIUM

## Risk Register (PgMP)
DEXTER / MIDAS — Program Risk Register (PgMP Standard)
Risk ID | Category | Risk Title | Description | Probability | Impact | Risk Score | Mitigation Strategy | WBS Owner (Story) | Team Owner
── | DATA INTEGRITY RISKS
R-DI-01 | Data Integrity | FRED API Silent Failure | FRED/SOFR returns stale or zero values. System proceeds without detecting corruption, poisoning the TIER_AUDIT and Gold layer regime outputs. | Medium | Critical | 🔴 HIGH | DL-3 (Dead-Letter + FAILED.json), OO-2 (Offline Observer), SILV-4 (GX expectation: price > 0, WALCL IS NOT NULL). CONVICTION_CAP reduced 0.2 per critical failure (floor 0.2). | DL-3, OO-1, OO-2 | Assurance & Ops
R-DI-02 | Data Integrity | Calculation Drift (Model Divergence) | Gemini and Claude lineages compute different regime labels or conviction caps from identical Silver inputs. No mechanism detects the drift until operator notices discrepancy. | High | High | 🔴 CRITICAL | BRNZ-3 (SHA-256 hash of decision fields at Bronze write). CALC_DRIFT alert when hash diverges for same run_date. All metric files must include model_name suffix (e.g. _CLAUDE_SONNET_4_6). | BRNZ-3 | Assurance & Ops
R-DI-03 | Data Integrity | Schema Evolution Breaking Downstream | New optional field added to ETL output breaks Silver DLT pipeline or GX expectations. Forward-compatible change treated as backward-incompatible. | Medium | High | 🟠 HIGH | SC-1 (schema registry), SC-2 (validate_schema with 3-tier: compatible / forward-compat / incompatible), SC-3 (SCHEMA_DRIFT report). BRNZ-2 (_rescued_data column). 3-run auto-learn for optional fields. | SC-1, SC-2, SC-3 | Assurance & Ops
── | OPERATIONAL RISKS
R-OP-01 | Operational | Cron UTC Offset | Cron fires at 01:45 ET instead of 05:45 ET (CRON-1 unfixed). ETL runs on yesterday's stale data. GMISR delivered before pre-market liquidity surge window. | High | High | 🔴 CRITICAL | CRON-1: fix cron to 10 45 * * 1-5 UTC. CRON-8: restrict to weekdays. This is currently the highest-urgency infrastructure item — affects every downstream wave. | CRON-1, CRON-8 | Assurance & Ops
R-OP-02 | Operational | API Key Exposure | FINNHUB_KEY, FRED_API_KEY, SLACK_WEBHOOK in plaintext in cron prompt body. Anyone with cron access has all credentials. Security breach risk. | Medium | Critical | 🔴 CRITICAL | CRON-2: migrate all keys to Azure VM environment variables or Key Vault. CRON-3: remove SLACK_WEBHOOK from prompt body to prevent double-fire. | CRON-2, CRON-3 | Assurance & Ops
R-OP-03 | Operational | Local Node Single Point of Failure | System runs on local K3s cluster / Linux machine. Hardware failure eliminates ETL output, NotebookLM corpus, and Parquet store with no failover. | Medium | High | 🟠 HIGH | OB-1 (SLA monitoring < 10min WARNING, <20min CRITICAL). OB-4 (30-day TTL + TIER_AUDIT indefinite retention). Wave 7 Databricks migration eliminates this risk entirely. | OB-1, OB-4, ARCH-1 | Assurance & Ops
── | MODELING RISKS
R-ML-01 | Modeling | HMM Premature Activation | Regime classifier (P4-1) activated before 30-trade Kelly gate passes. Model trained on insufficient labelled data. False regime signals trigger incorrect conviction caps. | Low | Critical | 🟠 HIGH | P4-3: hard gate — Kelly fraction requires >= 30 closed trade_log entries. Jira R-09 automation blocks P4-1 transition to Done without human sign-off. Fixed-fractional (1%) active until gate. | P4-1, P4-3 | Quant Lab
R-ML-02 | Modeling | Shadow Journal Drift (Epistemic Accuracy) | PHASE1_AGREEMENT (human vs model) drops below 60% for 30-day rolling window. Operator intuition diverging from system signals. Trades may be sized incorrectly. | Medium | High | 🟠 HIGH | GOLD-4 (backtest_integrity table). Rolling epistemic_accuracy computed from DAILY_STATE.md. Slack alert if < 60%. Phase 10 weekly audit reviews per-model agreement score. | GOLD-4 | Quant Lab
── | ARCHITECTURE RISKS
R-AR-01 | Architecture | ARCH-1 Blocking All Wave 7 | Unity Catalog provisioning (ARCH-1) is the absolute prerequisite for all Bronze/Silver/Gold/MCP work. Any delay cascades to all Wave 7 items simultaneously. | Medium | Critical | 🔴 CRITICAL | ARCH-1 first in Wave 7 sprint. Jira R-10 auto-blocks all Wave 7 stories until ARCH-1 = DONE. Databricks already connected (dbc-0df8fb6d-4908.cloud.databricks.com) — provisioning risk lower than greenfield. | ARCH-1 | Data Foundry
R-AR-02 | Architecture | Epic 21 Dual-Layer Duplication | Wave 2 (AWAP / local) and Wave 7 (DLT / cloud) implement similar Bronze→Silver logic independently, causing divergent results and wasted engineering effort. | Medium | High | 🟠 HIGH | SYNC-5 (annotation): Wave 2/3/6 items explicitly annotated as local equivalents of Medallion layers. SYNC-4 (v1.5 contract) defines which layer supersedes. Architecture review gate before Wave 7 sprint starts. | SYNC-5, SYNC-4 | Data Foundry

## Program Roadmap
DEXTER / MIDAS — Program Roadmap 2026-2027 (PgMP Phase-Gate Model)
Phase | Milestone | Wave(s) | Target Quarter | Epics in Scope | Key Gate | North Star Contribution | Status | Pts
Phase 1 Hardened Foundations | M0 — Infrastructure Stable | WAVE 0 | Q1 2026 (Mar) | ETL Bug Fixes, Docs, Infrastructure, Security | Cron fires at 05:45 ET daily. API keys in env vars. No duplicate Slack fire. | Punctuality: Structural prerequisite for all downstream waves. | IN PROGRESS | 29
Phase 1 Hardened Foundations | M1 — Error Visibility | WAVE 1 | Q2 2026 (Apr-May) | Dead-Letter Queue (DL-1 to DL-3), Offline Observer (OO-1 to OO-3) | FAILED_{date}.json written on every run. CONVICTION_CAP auto-reduced on critical failures. OO-2 observer live. | Data Integrity: Eliminates silent failures that would poison Gold layer regime outputs. | TO DO | 20
Phase 1 Hardened Foundations | M2 — Quality Gates | WAVE 2 | Q2 2026 (May-Jun) | AWAP Pattern (AW-1 to AW-4), Schema Compat (SC-1 to SC-3) | All modules pass pre/post-write audit. SCHEMA_DRIFT auto-detected. No malformed data in staging. | Data Integrity: Local equivalent of Medallion Gate 1/2. Prevents garbage-in to GMISR. | TO DO | 27
Phase 1 Hardened Foundations | M3 — Idempotency Gate | WAVE 3 | Q3 2026 (Jul) | Idempotency (ID-1 to ID-6) | --force-rerun on any date T-1 to T-5 produces binary-identical MANIFEST.json and TIER_AUDIT. | Reliability: Enables deterministic re-runs and audit trail. Local equivalent of Delta Lake ACID. | TO DO | 21
Phase 2 Corpus Intelligence | M4 — Corpus Enrichment | WAVE 4 | Q3 2026 (Aug-Sep) | Scrapling (SCRAP-1 to SCRAP-4) | Category A global sources (BoJ, PBOC, BoE, BCB, RBI) integrated into NEWS_CORPUS. SYNC_CONTRACT v1.4. | Breadth: Brief covers non-Western macro. NLLI velocity scoring across enriched corpus. | TO DO | 9
Phase 2 Corpus Intelligence | M5 — Alpha Signals | WAVE 5 | Q4 2026 (Oct-Nov) | GMISR v2.0, Scored Metrics (HDS/VPI/LFI/NLLI/PSI/CXOD), Model Delta, Econ Calendar, EDGAR v2.0, Polymarket | All 7 scored metrics live in TIER_AUDIT. GMISR Phase 5 includes Blocks 2.5, 2.7, 5, 10, 11. | Accuracy: System produces scored signals not raw text. Closes narrative-to-price arbitrage gap. | TO DO | 101
Phase 2 Corpus Intelligence | M6 — ML Readiness | WAVE 6 | Q4 2026 (Dec) | Parquet snapshot layer, DuckDB, Feature Store (Feast), HMM Classifier, Observability | Kelly Activation Gate: 30 closed trades in trade_log.parquet. HMM P4-1 accuracy >= 90% vs shadow journal. | Automation: Regime label sourced from model, not human. Circuit breaker = epistemic_accuracy < 60%. | TO DO | 115
Phase 3 Autonomous Orchestration | M7 — Medallion Architecture | WAVE 7 | Q1 2027 (Jan-Mar) | Databricks Unity Catalog, Bronze/Silver/Gold DLT, Great Expectations, Claude MCP Integration | ARCH-1 complete. midas.gold.* tables live. Claude queries Gold not text files. Calculation drift = 0. | Determinism: Single source of truth. All consumers (Claude, OpenClaw, dashboards) read same Gold table. | TO DO | 80
Phase 3 Autonomous Orchestration | M8 — Autonomous GMISR (North Star) | WAVE 8 | Q2 2027 | All waves integrated. OpenClaw cron fully autonomous. | 10 consecutive days: Slack ≤ 06:35 ET, PHASE1_AGREEMENT ≥ 90%, CRITICAL_FAILURES = 0, Cost ≤ $2.50/day. | ✅ NORTH STAR: Fully agentic daily macro brief. Human role = auditor only (circuit breaker). | PLANNED | 0

## JQL Filters & Team Boards
DEXTER / MIDAS — JQL Filters for Team Topology Boards (Jira)
Team (Topology) | Board Name | JQL Query | Purpose | Refresh
Sentinel Alpha | Alpha Stream Board | "Epic Link" IN (SCRAPLING, GMISR_V2.0, SCORED_METRICS, ADVANCED_SIGNALS, MODEL_DELTA, POLYMARKET_LAYER, ECON_CALENDAR, EDGAR_V2.0) OR "Epic Name" ~ "Scrapling" OR "Epic Name" ~ "GMISR" ORDER BY priority DESC | Direct alpha generation: news enrichment, scored metrics, GMISR synthesis, agentic workflows. | Daily
Data Foundry | Data Platform Board | "Epic Link" IN (IDEMPOTENCY, INFRASTRUCTURE, MEDALLION_ARCHITECTURE, BRONZE_LAYER, SILVER_LAYER, GOLD_LAYER, CLAUDE_MCP_INTEGRATION) OR summary ~ "Databricks" OR summary ~ "Unity Catalog" OR summary ~ "Delta Lake" ORDER BY priority DESC | Medallion architecture, DLT pipelines, Gold materialized views, Claude MCP wiring. | Daily
Assurance & Ops | Quality & Governance Board | "Epic Link" IN (ETL_BUG_FIXES, DOCS, SECURITY, DEAD-LETTER_QUEUE, OFFLINE_OBSERVER, AWAP_PATTERN, SCHEMA_COMPAT, OBSERVABILITY, GOVERNANCE) OR labels = "governance" ORDER BY priority DESC | Error visibility, quality gates, cron stability, schema compat, SYNC_CONTRACT governance. | Daily
Quant Lab | ML & Analytics Board | "Epic Link" IN (PARQUET_SNAPSHOT_LAYER, DUCKDB_ANALYTICS_LAYER, FEATURE_STORE, ML_REGIME_CLASSIFIER, TRACK_B_SHADOW) OR summary ~ "HMM" OR summary ~ "hmmlearn" OR summary ~ "Kelly" ORDER BY priority DESC | Parquet schema, DuckDB dashboards, Feast feature store, HMM regime classifier, shadow pipeline. | Sprint
All Teams (Program) | North Star Dashboard | project = "MIDAS" AND (labels = "agent-integrated" OR summary ~ "06:35" OR summary ~ "Kelly" OR summary ~ "CONVICTION_CAP" OR summary ~ "Gold" OR labels = "governance") ORDER BY priority DESC | Cross-team view of items directly contributing to the Autonomous GMISR North Star (M8). | Weekly
All Teams (Program) | Critical Gates View | project = "MIDAS" AND (id IN (CRON-1, CRON-2, ARCH-1, DL-3, SC-2, ID-3, SILV-4, GOLD-1, MCP-1, P4-3) OR labels = "gate" OR priority = Critical) ORDER BY priority DESC, created ASC | Program phase-gate blockers only. Items that block the next wave from starting. | Daily
Assurance & Ops | Calculation Drift Monitor | project = "MIDAS" AND (labels = "calculation-drift" OR summary ~ "hash" OR summary ~ "model_name" OR summary ~ "BRNZ-3" OR id = "GOLD-4") ORDER BY updated DESC | All items related to the model-name suffix and calculation drift detection protocol. | Weekly

## Wave 7 Jira Import
DEXTER / MIDAS — Wave 7 Jira Import: Medallion Architecture (Databricks)
Issue ID | Issue Type | Epic Link | Epic Name | Wave | Team | Summary | Priority | Status | Story Pts | Acceptance Criteria (Key)
ARCH-1 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Data Foundry | Provision Databricks workspace and Unity Catalog — midas.bronze/silver/gold namespaces | Critical | OPEN | 3 | midas catalog exists. bronze/silver/gold schemas created. ETL SP has WRITE on bronze. Claude MCP SP has READ on gold only. ✅ BLOCKS all other Wave 7 items.
ARCH-2 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Sentinel Alpha | Define canonical entity resolution schema — ticker normalisation map | High | OPEN | 3 | ENTITY_MAP table in Unity Catalog. GC=F→COM_GOLD, DX-Y.NYB→FX_DXY mapped. All Silver tables join through ENTITY_MAP. Calculation difference problem resolved.
ARCH-3 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Sentinel Alpha | Define temporal alignment standard — ISO-8601 UTC across all layers | High | OPEN | 2 | timestamp_normalise() utility. All ingested timestamps → ingest_timestamp_utc. Documented in SYNC_CONTRACT v1.5.
BRNZ-1 | Story | MIDAS-133 | Bronze Layer | WAVE 7 | Sentinel Alpha | Register ETL flat-file outputs as Delta Lake Bronze tables in Unity Catalog | High | OPEN | 5 | 9 Bronze tables: fred_summary, market_data, treasury_auctions, dollar_decomp, sec_ftd, edgar_filings, news_corpus, econ_calendar, polymarket_signals. Append-only. Lineage via _metadata.file_path.
BRNZ-2 | Story | MIDAS-133 | Bronze Layer | WAVE 7 | Sentinel Alpha | Add _rescued_data column handling for schema mismatches at Bronze ingest | Medium | OPEN | 3 | DLT routes mismatched fields to _rescued_data. Daily Slack alert if rescued_count > 0 on critical tables. Equivalent of local SC-3 SCHEMA_DRIFT report.
BRNZ-3 | Story | MIDAS-133 | Bronze Layer | WAVE 7 | Sentinel Alpha | Implement calculation hash (Gate 4) on Bronze model outputs | Critical | OPEN | 3 | SHA-256 hash of (regime_label, conviction_cap, dollar_composite) at Bronze write. CALCULATION_DRIFT Slack alert on hash divergence. Solves Gemini vs Claude model output drift.
SILV-1 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Sentinel Alpha | Build Silver DLT pipeline — refined_market_prices streaming table | High | OPEN | 5 | 3 gates enforced. EXPECT (price > 0), EXPECT (ABS(brent-wti) < 15). Entity map join. midas.silver.refined_market_prices with source_origin lineage.
SILV-2 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Sentinel Alpha | Build Silver DLT pipeline — sovereign_stress_monitor streaming table | High | OPEN | 5 | DOLLAR_DECOMP 4-layer completeness check. All 4 layers non-null before day marked COMPLETE. QUARANTINE for fra_ois anomalies.
SILV-3 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Sentinel Alpha | Build Silver DLT pipeline — settlement_risk_indices streaming table | High | OPEN | 3 | SEC_FTD zero-price rows handled (newly listed securities). EDGAR entity names normalised via ENTITY_MAP. TQQQ_FTD as first-class column.
SILV-4 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Sentinel Alpha | Implement Great Expectations suite — 7 named expectations against ETL file types | High | OPEN | 8 | 7 named expectations active. GX Data Docs generated daily. All Silver tables have active GX suite. Failed rows logged + traceable. ≥99.5% pass rate. ✅ GATES all Gold layer work.
GOLD-1 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Sentinel Alpha | Build mkt_regime_final Gold materialized view — REGIME_RULES.md as code | High | OPEN | 5 | Regime A/B/C SQL logic matches REGIME_RULES.md exactly. Gate 5 quorum: all critical Silver sources COMPLETE for date. Low_Confidence flag when stale. Reproducible from Silver inputs.
GOLD-2 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Sentinel Alpha | Build risk_sentinel_status Gold materialized view — SOUL.md §3/§4 as code | High | OPEN | 5 | CONVICTION_CAP graduated logic: 1.0→0.5→0.4→0.0. RISK_SENTINEL_TRIGGER conditions match SOUL.md §4. Claude MCP queries this instead of TIER_AUDIT text.
GOLD-3 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Sentinel Alpha | Build liquidity_gate Gold materialized view — MACRO_TIERS §Tier -2 as code | High | OPEN | 3 | net_liq_b = WALCL - TGA - RRP. is_blocked BOOL. gate_status OPEN/RESTRICTED/CLOSED. max_positions per regime. Phase 2 GatePass reads this directly.
GOLD-4 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Sentinel Alpha | Build backtest_integrity Gold table — DAILY_STATE.md shadow journal as first-class asset | High | OPEN | 3 | Rolling epistemic_accuracy (30-day). Slack alert if < 60%. Feeds HMM training as label source. Primary ML feedback loop for regime classifier validation.
GOLD-5 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Sentinel Alpha | Build sync_audit Gold table — DEXTER_SYNC_CONTRACT.md compliance as code | Medium | OPEN | 2 | Daily diff of ETL TRIGGERS dict vs SOUL §3 canonical thresholds. SYNC_VIOLATION rows written on any drift. Replaces manual SYNC_CONTRACT audit.
MCP-1 | Story | MIDAS-133 | Claude MCP Integration | WAVE 7 | Sentinel Alpha | Wire Claude MCP Databricks connector to Gold tables — read-only service principal | High | OPEN | 3 | Claude queries midas.gold.* via MCP. Claude does NOT compute regime — queries mkt_regime_final. Calculation differences between Gemini and Claude lineages eliminated.
MCP-2 | Story | MIDAS-133 | Claude MCP Integration | WAVE 7 | Sentinel Alpha | Add Gold table query examples to Phase 0 and Phase 2 prompts in manifest | Medium | OPEN | 2 | MIDAS_SENTINEL_PROMPT_LIBRARY v2026.5. Gold table takes precedence over TIER_AUDIT text when both available. TIER_AUDIT remains fallback when MCP unavailable.
SYNC-4 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Sentinel Alpha | Update SYNC_CONTRACT v1.5 — Medallion layer mapping and temporal alignment standard | High | OPEN | 2 | Medallion section added. Gold supersedes text files when available. Temporal alignment: ISO-8601 UTC. Wave/item cross-reference table included.
SYNC-5 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Sentinel Alpha | Annotate existing Wave 2/3/6 items with Medallion layer equivalence notes | Low | OPEN | 1 | AW-1/2/3/4 annotated as local Bronze→Silver Gate equivalents. Prevents dual-implementation of same logic in local and cloud layers.
Wave 7 Total Stories: 19