## Fisher-Rao FIL Import
DEXTER / MIDAS — Fisher–Rao FIL Epic + Stories: Jira Import (2026-03-31)
Source: FisherRao_Applied_to_Dexter_Midas.md ¦ Integrates with WBS v8 ¦ Link annotations show impact on existing stories
Issue ID | Issue Type | Epic Link | Epic Name | Wave | Team (Topology) | Summary | Priority | Status | Pts | Labels | Linked To (Blocks / Blocked-By / Updates / Gates) | Acceptance Criteria + Fisher Framework Reference
MIDAS-FIL | Epic | FIL | Fisher Info Layer | WAVE 5/6/7 | Quant Lab / Data Foundry / Assurance & Ops | Fisher–Rao information geometry layer: rolling Fisher matrix, eigenvalue dynamics, geometry-based HMM observation upgrade (FIL-6 updates P4-1), feature pruning, STRUCTURE_SHIFT alerting. Source: FisherRao_Applied_to_Dexter_Midas.md | High | OPEN | 39 | fisher-rao,wave-6,wave-7 | BLOCKS/UPDATES: P4-1, GOLD-1, GOLD-2, GOLD-4 ¦ BLOCKED BY: ARCH-1, SILV-4, P1-1, P3-1 | All 8 FIL stories complete. fisher_regime_engine live in midas.gold. PHASE1_AGREEMENT ≥90% geometry-HMM vs shadow journal. Pruned feature set in SOUL.md §3.2. STRUCTURE_SHIFT alerting active.
FIL-1 | Story | FIL | Fisher Info Layer | WAVE 6 | Quant Lab | Implement rolling empirical Fisher matrix over gmisr_metrics Parquet | High | OPEN | 8 | wave-6,fisher-rao | BLOCKED BY: P1-1 (Parquet schema) ¦ BLOCKS: FIL-2, FIL-6 | 20-day rolling F̂=(1/N)Σ∇logp·∇logp⊤ per trade_date. EWMA variant. Output: fisher_features/ Parquet partition. Windowed per doc §27 Step 1.
FIL-2 | Story | FIL | Fisher Info Layer | WAVE 6 | Quant Lab | Extract geometry feature vector z_t = (λ1, λ2, trace, rank, alignment, dλ/dt, drank/dt) | High | OPEN | 5 | wave-6,fisher-rao | BLOCKED BY: FIL-1 ¦ BLOCKS: FIL-3, FIL-5, FIL-6, FIL-7, FIL-8 | Spectral decomp daily. rank=count(λ>0.10·λ1). alignment=¦Q_t[:,−1]·Q_{t-1}[:,−1]¦. eigenvalue_velocity=λ1_t−λ1_{t-1}. rank_dynamics=rank_t−rank_{t-1}. Implements doc §26.
FIL-3 | Story | FIL | Fisher Info Layer | WAVE 6 | Quant Lab | Add fisher_lambda1/2, trace, rank, alignment, velocity, rank_dynamics to Parquet schema v1.1 | High | OPEN | 3 | wave-6,fisher-rao | BLOCKED BY: FIL-2, P1-2 (schema v1.0) ¦ BLOCKS: FIL-4, FIL-6 | Schema v1.1. 7 new nullable columns (DOUBLE/INT). MANIFEST schema_version=1.1. Migration script.
FIL-4 | Story | FIL | Fisher Info Layer | WAVE 7 | Data Foundry | Build midas.gold.fisher_regime_engine materialized view — geometry signals + conviction multiplier | High | OPEN | 5 | wave-7,fisher-rao | BLOCKED BY: FIL-3, GOLD-1, SILV-4, ARCH-1 ¦ UPDATES: GOLD-1, GOLD-2 | Signals: ALPHA_WINDOW/CROWDING_EXIT/TRANSITION_REBALANCE/HOLD. fisher_conviction_multiplier: 1.0/0.7/0.4/0.2. Geometry taxonomy: CONSENSUS/TRANSITION/FRAGMENTATION/CROWDING/EMERGENCE. Maps A=CONSENSUS¦EMERGENCE, B=TRANSITION, C=FRAGMENTATION¦CROWDING.
FIL-5 | Story | FIL | Fisher Info Layer | WAVE 6 | Assurance & Ops | Add FISHER_INFO_SCORE and EXECUTABILITY_FLAG to TIER_AUDIT; compute ALPHA_SCORE per metric | Medium | OPEN | 3 | wave-6,fisher-rao | BLOCKED BY: FIL-2 ¦ LINKED TO: DL-3, GOLD-2 | FISHER_INFO_SCORE 0-1 rolling 20d. EXECUTABILITY_FLAG: CLEAN¦LATENT¦STALE¦ILLIQUID. ALPHA_SCORE = Fisher_info × executability_weight. Threshold >0.5 for HMM eligibility. Implements doc: 'Alpha Score = Information × Executability'.
FIL-6 | Story | FIL | Fisher Info Layer | WAVE 6 | Quant Lab | Upgrade P4-1 HMM: replace raw metric obs vector with geometry feature vector z_t | High | OPEN | 8 | wave-6,fisher-rao | BLOCKED BY: FIL-3, FIL-8, P3-1 (Feast) ¦ UPDATES: P4-1 ¦ GATE: P4-3 Kelly | Obs: [HDS,VPI,LFI,VX_ratio,FRA-OIS,net_liq_roc,NLLI] → z_t=(λ1,λ2,trace,rank,alignment,dλ1,drank). 5-state geometry taxonomy; outputs A/B/C for downstream compat. Validation ≥90% PHASE1_AGREEMENT. Kelly Gate (P4-3) still applies. IQ-1 (FRA-OIS Δ1/Δ2) promoted as geometry-native eigenvalue-velocity proxy.
FIL-7 | Story | FIL | Fisher Info Layer | WAVE 5 | Assurance & Ops | STRUCTURE_SHIFT Slack alert: eigenvector_alignment < 0.85 for 2 consecutive days | Medium | OPEN | 2 | wave-5,fisher-rao | BLOCKED BY: FIL-2 ¦ LINKED TO: OB-1 (SLA), GOV-4 (sync) | Silent-failure detector. Fires regardless of regime label change. Alert: STRUCTURE_SHIFT — alignment={val:.3f} d2. Factor rotation. Reduce directional exposure. Implements doc: 'Rotation of eigenvectors → rebalance exposures'.
FIL-8 | Story | FIL | Fisher Info Layer | WAVE 6 | Quant Lab | Fisher-based feature pruning: off-diagonal collinearity audit of HDS/NLLI/NDI/CCS/CXOD | Medium | OPEN | 5 | wave-6,fisher-rao | BLOCKED BY: FIL-1 ¦ AUDIT: SCORE-1 (HDS), SCORE-4 (NLLI), GMISR-6 (NDI) | Off-diag test: g_ij > 0.70·min(g_ii,g_jj) → collapse to higher-executability feature. Expected: NLLI>HDS, NDI removed, CXOD>CCS. Pruned set in SOUL.md §3.2. Implements doc: 'Fisher metric reveals collinearity via near-singular matrix + flat directions'.
▶ LINK ANNOTATIONS — Existing WBS Stories Affected by FIL Integration
Existing Story ID | Relationship Type | Integration Note — What Changes and Why
P4-1 | UPDATED BY FIL-6 | Raw metric obs vector replaced by z_t=(λ1,λ2,trace,rank,alignment,dλ1,drank). HMM retrained on geometry features. 5-state taxonomy; A/B/C outputs preserved. Kelly Gate P4-3 still applies.
GOLD-1 | EXTENDED BY FIL-4 | fisher_regime_engine extends mkt_regime_final: adds geometry_signal + fisher_conviction_multiplier columns.
GOLD-2 | UPDATED BY FIL-4/5 | conviction_cap_final = SOUL_cap × fisher_conviction_multiplier. SOUL.md 0.4 floor preserved; Fisher provides graduated response [0.2–1.0] based on geometry state.
GOLD-4 | LINKED: FIL-6 | geometry-HMM outputs feed backtest_integrity for shadow journal epistemic_accuracy validation loop.
SCORE-1 | AUDIT: FIL-8 | HDS likely collinear with NLLI in Fisher space. FIL-8 off-diagonal test may remove HDS from HMM input.
SCORE-4 | PROMOTED: FIL-8 | NLLI survives Fisher pruning — velocity preferred over level. Promoted as geometry-native proxy.
GMISR-6 | AUDIT: FIL-8 | NDI likely collinear with HDS in Fisher space. FIL-8 collinearity test determines HMM inclusion.
IQ-1 | PROMOTED: FIL-6 | FRA-OIS Δ1 (velocity) and Δ2 (acceleration) are eigenvalue-velocity proxies. Highest-priority geometry feature.
IQ-10 | PROMOTED: FIL-4 | GEX treated as eigenvector conditioning variable (not additive signal). Determines which Fisher eigenvectors are active. Positive GEX = PINNING suppresses eigenvector rotation.
SILV-4 | GATE FOR: FIL-4 | FIL-4 (fisher_regime_engine) blocked until SILV-4 GX suite passes at ≥99.5% on Silver layer.
ARCH-1 | GATE FOR: FIL-4 | FIL-4 gold view cannot be built until ARCH-1 provisions Unity Catalog midas namespaces.
P1-1 | GATE FOR: FIL-1 | FIL-1 rolling Fisher computation requires Parquet schema locked via P1-1.
P3-1 | GATE FOR: FIL-6 | FIL-6 HMM upgrade requires Feast feature store P3-1 active for point-in-time correct training sets.
P4-3 | GATE FOR: FIL-6 | Geometry-HMM (FIL-6) still subject to 30-trade Kelly Gate P4-3. Fixed-fractional until gate passes.
▶ JQL FILTER — Fisher-Rao Layer Board
"Epic Link" = FIL OR labels = "fisher-rao" OR id IN (FIL-1,FIL-2,FIL-3,FIL-4,FIL-5,FIL-6,FIL-7,FIL-8) ORDER BY priority DESC, created ASC
▶ DEPENDENCY CHAIN: FIL Stories Must Execute In This Order
P1-1 (Parquet schema) → FIL-1 (Fisher matrix) → FIL-2 (geometry features) → FIL-8 (feature pruning) + FIL-7 (STRUCTURE_SHIFT alert) + FIL-5 (TIER_AUDIT scores) → FIL-3 (Parquet schema v1.1) → FIL-6 (HMM upgrade, also needs P3-1 Feast) → FIL-4 (Gold view, also needs GOLD-1, SILV-4, ARCH-1) ¦ FIL-6 still subject to P4-3 Kelly Gate (30 trades) ¦ FIL-4 still subject to ARCH-1 Unity Catalog provisioning

## Jira Import — Full Backlog
DEXTER / MIDAS — Jira Import: Full Program Backlog (v9, 2026-04-01)
Source: DEXTER_MIDAS_WBS_v8_FINAL.csv + Wave 8 agentic stack additions ¦ Team 0: SE-Infra added ¦ Wave 7 reassigned to Data Foundry ¦ 20 new Wave 8 stories (64 pts) ¦ Total: 169 stories
Issue ID
▶ WAVE 0 — Team 0: SE-Infra (CRON) + Assurance & Ops
CRON-1 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Team 0: SE-Infra | Fix cron UTC offset: 45 5 → 10 45 (fires at 01:45 ET, not 05:45 ET) | High | OPEN | 1 | wave-0 | Current: 45 5 = 01:45 ET. Target: 10 45 * * 1-5 UTC = 05:45 ET. Fix before next market day.
CRON-2 | Story | MIDAS-4 | Security | WAVE 0 | Team 0: SE-Infra | Remove API keys from cron prompt body — move to env vars | Critical | OPEN | 2 | wave-0,security | FINNHUB_KEY, FRED_API_KEY, SLACK_WEBHOOK in plaintext. Move to Azure VM env vars or Key Vault.
CRON-3 | Story | MIDAS-4 | Security | WAVE 0 | Team 0: SE-Infra | Fix SLACK_WEBHOOK double-fire — remove from cron prompt body | High | OPEN | 1 | wave-0,security | SLACK_WEBHOOK in both prompt body and delivery config. Remove from prompt body.
CRON-4 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Team 0: SE-Infra | Add dexter_notebooklm_upload.py as cron step 3 (after ETL, before Phase 0) | High | OPEN | 1 | wave-0 | HEARTBEAT 05:55 step. Must run after ETL creates files and before Phase 0 reads them.
CRON-5 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Team 0: SE-Infra | Add OpenClaw Phase 0-5 as cron step 6 | High | OPEN | 2 | wave-0,agent-integrated | Phase 0→0.5→1→2→3→4→5 must be scheduled after NotebookLM upload completes.
CRON-6 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Team 0: SE-Infra | Add DAILY_STATE.md update as cron step 7 (after Phase 5) | Med | OPEN | 1 | wave-0 | Phase 5 output feeds DAILY_STATE.md. Currently unscheduled.
CRON-7 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Team 0: SE-Infra | Rename feedmd_config_03-01-2026.yml to date-agnostic name | Med | OPEN | 1 | wave-0 | Date-stamped config breaks reproducibility.
CRON-8 | Story | MIDAS-3 | Infrastructure | WAVE 0 | Team 0: SE-Infra | Restrict cron to weekdays (1-5) and confirm weekend intent | Med | OPEN | 1 | wave-0 | Currently * * * = 7 days/week. Weekend ETL produces stale data.
DOCS-AGENTS | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | AGENTS.md v1.1 — model, ETL spec, conflict logic, phase order | Med | DONE | 2 | wave-0 | Done.
DOCS-HEARTBEAT | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | HEARTBEAT.md v1.1 — 11 fixes | Med | DONE | 2 | wave-0 | Done.
DOCS-MACRO | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | MACRO_TIERS v3.2 — ETL 1.7.5.6 sync | Med | DONE | 2 | wave-0 | Done.
DOCS-MANIFEST | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | MIDAS_SENTINEL_PROMPT_LIBRARY v2026.4 — 3 corrections | Med | DONE | 2 | wave-0 | Done.
DOCS-NAMING | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | Naming standardisation — Dexter ETL / Midas Sentinel | Med | DONE | 1 | wave-0 | Done.
DOCS-OC-SOUL | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | OPENCLAW_SOUL 2026.3.22 — 6 logic fixes | Med | DONE | 2 | wave-0 | Done.
DOCS-REGIME | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | REGIME_RULES v2.3 — Dollar Decomp wired into weighting | Med | DONE | 2 | wave-0 | Done.
DOCS-SOUL | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | SOUL v2.4 — §3.1 Dollar Decomp supplement | Med | DONE | 2 | wave-0 | Done.
ETL-1.7.5.5 | Story | MIDAS-1 | ETL Bug Fixes | WAVE 0 | Assurance & Ops | CFTC Layer 4 — partial 404 fix (Socrata SODA endpoint) | High | DONE | 1 | wave-0 | Done.
ETL-1.7.5.6 | Story | MIDAS-1 | ETL Bug Fixes | WAVE 0 | Assurance & Ops | CFTC Layer 4 — confirmed live endpoint /api/v3/ | High | DONE | 2 | wave-0 | Done.
SYNC-1.3 | Story | MIDAS-2 | Docs | WAVE 0 | Assurance & Ops | DEXTER_SYNC_CONTRACT v1.3 — CFTC endpoint + version pairing | Med | DONE | 1 | wave-0 | Done.
▶ WAVE 1 — Assurance & Ops (Error Visibility)
DL-1 | Story | MIDAS-5 | Dead-Letter Queue | WAVE 1 | Assurance & Ops | Define DeadLetterEntry dataclass and criticality map | High | DONE | 3 | wave-1 | Done.
DL-2a | Story | MIDAS-5 | Dead-Letter Queue | WAVE 1 | Assurance & Ops | Thread dead-letter through run_fred() and run_treasury() (M1/M2) | High | DONE | 2 | wave-1 | Done.
DL-2b | Story | MIDAS-5 | Dead-Letter Queue | WAVE 1 | Assurance & Ops | Thread dead-letter through run_market() and run_fed_and_dtcc() (M3/M5) | High | DONE | 2 | wave-1 | Done.
DL-2c | Story | MIDAS-5 | Dead-Letter Queue | WAVE 1 | Assurance & Ops | Thread dead-letter through run_news() and run_calendars() (M7/M6) | High | OPEN | 2 | wave-1 | Two remaining function signatures need dead_letters param.
DL-3 | Story | MIDAS-5 | Dead-Letter Queue | WAVE 1 | Assurance & Ops | Write FAILED_{date}.json + DATA_FAILURES block in TIER_AUDIT | High | OPEN | 3 | wave-1,gate | CONVICTION_CAP reduced 0.2 per critical failure (floor 0.2). ✅ PHASE 1 GATE.
OO-1 | Story | MIDAS-6 | Offline Observer | WAVE 1 | Assurance & Ops | Define OBSERVATION_RULES dict per module | Med | DONE | 2 | wave-1 | Done.
OO-2 | Story | MIDAS-6 | Offline Observer | WAVE 1 | Assurance & Ops | Implement run_offline_observer() as Module 9.5 | High | OPEN | 5 | wave-1 | Runs after all modules, before build_tier_audit().
OO-3 | Story | MIDAS-6 | Offline Observer | WAVE 1 | Assurance & Ops | Inject observation results into TIER_AUDIT and completion banner | High | OPEN | 3 | wave-1 | Pass observations to build_tier_audit(). Add DATA_QUALITY_REPORT section.
▶ WAVE 2 — Assurance & Ops (Quality Gates / AWAP)
AW-1 | Story | MIDAS-7 | AWAP Pattern | WAVE 2 | Assurance & Ops | Implement staging directory and promote() helper | High | OPEN | 3 | wave-2 | Staging dir pattern for atomic promotes.
AW-2 | Story | MIDAS-7 | AWAP Pattern | WAVE 2 | Assurance & Ops | Implement pre-write input audit (Audit step 1) | High | OPEN | 8 | wave-2 | audit_input(module, data, rules). BLOCKED BY: DL-3.
AW-3 | Story | MIDAS-7 | AWAP Pattern | WAVE 2 | Assurance & Ops | Implement post-write output audit (Audit step 2) | High | OPEN | 5 | wave-2 | audit_output(staged_path, rules). Pass → promote(). Fail → AUDIT_FAILED.
AW-4 | Story | MIDAS-7 | AWAP Pattern | WAVE 2 | Assurance & Ops | Implement three audit failure strategies (Fail/Dispatch/Ignore) | High | OPEN | 5 | wave-2 | Per-module configurable strategy.
SC-1 | Story | MIDAS-8 | Schema Compat | WAVE 2 | Assurance & Ops | Define expected schemas for all external API responses | High | OPEN | 3 | wave-2 | SCHEMAS dict in schema_registry.py.
SC-2 | Story | MIDAS-8 | Schema Compat | WAVE 2 | Assurance & Ops | Implement validate_schema() and inject into fetch steps | High | OPEN | 5 | wave-2 | Three outcomes: compatible; forward-compatible; backward-incompatible.
SC-3 | Story | MIDAS-8 | Schema Compat | WAVE 2 | Assurance & Ops | Write SCHEMA_DRIFT report and auto-update optional field registry | Med | OPEN | 3 | wave-2 | SCHEMA_DRIFT_{date}.txt when new optionals appear.
▶ WAVE 3 — Data Foundry (Idempotency)
ID-1 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | Define idempotency granularity and document the contract | High | DONE | 3 | wave-3 | Done.
ID-2 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | Fix FRED_SUMMARY append bug — most urgent idempotency violation | High | DONE | 2 | wave-3 | Done.
ID-3 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | Implement atomic write via stage-then-rename (write_atomic) | High | OPEN | 5 | wave-3,gate | ✅ PHASE 1 GATE. BLOCKED BY: AW-2.
ID-4 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | Add run MANIFEST.json with schema version and ETL script hash | High | OPEN | 5 | wave-3 | Schema version + SHA-256 of ETL script in manifest.
ID-5 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | Make EDGAR incremental with delta-column state file (edgar_state.json) | Med | OPEN | 5 | wave-3 | 14-day backfill window. Eliminates ghost-filing problem.
ID-6 | Story | MIDAS-9 | Idempotency | WAVE 3 | Data Foundry | --force-rerun flag and idempotency test procedure | Med | OPEN | 3 | wave-3 | Same date rerun produces binary-identical output.
▶ WAVE 4 — Sentinel Alpha (Scrapling / Corpus Enrichment)
SCRAP-1 | Story | MIDAS-10 | Scrapling | WAVE 4 | Sentinel Alpha | Refactor scrapling_news.py — Category A sources only | High | OPEN | 5 | wave-4 | BoJ, PBOC, BoE, BCB, RBI, SAMA, Caixin, Risk.net, Trading Economics, Al Jazeera.
SCRAP-2 | Story | MIDAS-10 | Scrapling | WAVE 4 | Sentinel Alpha | Write merge_scrapling_into_corpus.py — append §SCRAPLING_SUPPLEMENT | High | OPEN | 5 | wave-4 | Append to NEWS_CORPUS_{date}.txt before NotebookLM upload.
SCRAP-3 | Story | MIDAS-10 | Scrapling | WAVE 4 | Sentinel Alpha | Document scrapling data lineage in SYNC_CONTRACT v1.4 | Med | OPEN | 2 | wave-4 | Map Category A sources to MACRO_TIERS tiers.
SCRAP-4 | Story | MIDAS-10 | Scrapling | WAVE 4 | Sentinel Alpha | Wire scrapling Category A sources into MACRO_TIERS tier routing | Med | OPEN | 3 | wave-4 | Update MACRO_TIERS v3.3.
▶ WAVE 5 — Sentinel Alpha (GMISR v2.0 / Scored Metrics)
DELTA-1 | Story | MIDAS-12 | Model Delta | WAVE 5 | Sentinel Alpha | Add Claude (Anthropic API) as Lineage B agent in AGENTS.md | High | OPEN | 3 | wave-5 | Claude as second lineage alongside Gemini.
DELTA-2 | Story | MIDAS-12 | Model Delta | WAVE 5 | Sentinel Alpha | Write Phase 3.5 delta synthesiser prompt | High | OPEN | 5 | wave-5 | Cross-model comparison prompt.
GMISR-1 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add GICS codes to SENTENCE_DIRECTIVE setups (Phase 4 prompt) | Med | OPEN | 2 | wave-5 | Every driver must carry full GICS code.
GMISR-2 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add qualitative invalidation condition per driver | Med | OPEN | 2 | wave-5 | INVALIDATION: [specific condition]. Phase 4 prompt.
GMISR-3 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add Catalyst Map 24h/48h/72h as Block 10 to Phase 5 GMISR schema | High | OPEN | 3 | wave-5 | Forward-looking catalyst timeline.
GMISR-4 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add structured pair trade output to Phase 5 | High | OPEN | 3 | wave-5 | Long/Short with GICS sector logic.
GMISR-5 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add per-claim source citation (Block 11 Data Lineage) to Phase 5 | Med | OPEN | 2 | wave-5 | Cite source per major claim.
GMISR-6 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add NDI (Narrative Divergence Index) to Phase 3 | Med | OPEN | 2 | wave-5 | Count distinct narrative clusters 0-1 score.
GMISR-7 | Story | MIDAS-11 | GMISR v2.0 | WAVE 5 | Sentinel Alpha | Add Narrative Velocity / NLLI scoring to Phase 3 | Med | OPEN | 3 | wave-5 | Velocity of emerging vs established clusters.
SCORE-1 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement HDS auto-scoring in run_news() | High | OPEN | 5 | wave-5 | Headline Density Score per tier.
SCORE-2 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement VPI (Volatility Pricing Index) in build_tier_audit() | High | OPEN | 3 | wave-5 | VIX_spot / 5-day realized vol proxy.
SCORE-3 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement LFI (Liquidity Friction Index) in build_tier_audit() | High | OPEN | 5 | wave-5 | FRA-OIS + BDC discount + EDGAR 8-K withdrawal count.
SCORE-4 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement NLLI (Narrative Lag-Lead Indicator) in run_news() | High | OPEN | 5 | wave-5 | Compare tier headline counts to prior 5-run rolling average.
SCORE-5 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement CCS (Cross-Correlation Score) in run_market() | Low | OPEN | 5 | wave-5 | Correlation between ratio-pair movements vs broad index.
SCORE-6 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement CXOD (Cross-Asset Order Delta) in run_market() | Low | OPEN | 3 | wave-5 | (USO 1d return) - (QQQ 1d return) signed flow divergence.
SCORE-7 | Story | MIDAS-13 | Scored Metrics | WAVE 5 | Sentinel Alpha | Implement PSI (Policy Sensitivity Index) in build_tier_audit() | Low | OPEN | 5 | wave-5 | GDP revision + FRA-OIS + high-impact events + guidance revisions.
IQ-5 | Story | MIDAS-14 | Advanced Signals | WAVE 5 | Sentinel Alpha | COT/CFTC positioning (Module 6b Layer 4) — LIVE | Med | DONE | 3 | wave-5 | Done.
T4-8 | Story | MIDAS-14 | Advanced Signals | WAVE 5 | Sentinel Alpha | Gold/NASDAQ absolute >0.30 flag in TIER_AUDIT | Med | OPEN | 2 | wave-5 | Ratio flag.
T4-10 | Story | MIDAS-14 | Advanced Signals | WAVE 5 | Sentinel Alpha | RATIO_SIGNALS named section in TIER_AUDIT — schema 2.0.0.0 | Med | OPEN | 3 | wave-5 | Named section for all ratio signals.
▶ WAVE 6 — Quant Lab (ML / Parquet) + Assurance & Ops (Observability)
OB-1 | Story |  | Observability | WAVE 6 | Assurance & Ops | SLA monitoring — per-module timing + elapsed alert (SLA Misses Detector) | Med | OPEN | 3 | wave-6 | Total run > 10min = WARNING, > 20min = CRITICAL Slack.
OB-2
OB-3 | Story |  | Observability | WAVE 6 | Assurance & Ops | Filter Interceptor — NEWS_CORPUS UNCLASSIFIED rate per feed | Med | OPEN | 2 | wave-6 | Flag feeds >40% UNCLASSIFIED for quality review.
OB-4 | Story |  | Observability | WAVE 6 | Assurance & Ops | Data retention policy — TTL for raw ETL outputs + cleanup script | Low | OPEN | 2 | wave-6 | 30-day TTL for raw; indefinite for TIER_AUDIT and Parquet.
OB-5 | Story |  | Observability | WAVE 6 | Assurance & Ops | Fine-grained lineage SOURCE_MAP — shared scope with IQ-7 | Low | OPEN | 1 | wave-6 | source_hash per Parquet row linking to ETL run.
P1-1 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Add write_parquet_snapshot() to ETL main() | High | OPEN | 3 | wave-6 | 28 typed columns partitioned by run_date. ETL bump to 1.8.0.0.
P1-2 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Define and lock GMISR_METRICS Parquet schema v1.0 | High | OPEN | 2 | wave-6 | schema_registry.py entry. Schema version in MANIFEST.json.
P1-3 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Add phase1_agreement and actual_spx_5d ML label columns | High | OPEN | 3 | wave-6 | BLOCKED BY: P1-1.
P1-4 | Story |  | Parquet snapshot layer | WAVE 6 | Quant Lab | Write backfill_parquet.py — populate history from existing run archive | Med | OPEN | 5 | wave-6 | Backfill from existing TIER_AUDIT archive.
P2-1 | Story |  | DuckDB analytics layer | WAVE 6 | Sentinel Alpha | Set up DuckDB + Evidence.dev local dashboard | High | OPEN | 3 | wave-6 | Local analytics layer. BLOCKED BY: P1-1.
P2-2 | Story |  | DuckDB analytics layer | WAVE 6 | Sentinel Alpha | Build 30/60/90-day regime and metrics dashboard | Med | OPEN | 3 | wave-6 | Regime timeline + scored metrics heatmap.
P3-1 | Story |  | Feature store (ML bridge) | WAVE 6 | Quant Lab | Implement Feast feature store — point-in-time correct training sets | Low | OPEN | 5 | wave-6 | pip install feast. Prerequisite for P4-1. BLOCKED BY: P1-1, P1-2.
P4-1 | Story |  | ML regime classifier | WAVE 6 | Quant Lab | Build regime classifier v1.0 — HMM on scored metrics | Low | OPEN | 8 | wave-6,gate | BLOCKED BY: P3-1. Kelly activation gate (≥30 labelled runs). ✅ PHASE 2 GATE.
P4-2 | Story |  | ML regime classifier | WAVE 6 | Quant Lab | Build SENTENCE_DIRECTIVE outcome tracker — P&L attribution log | Med | OPEN | 5 | wave-6 | trade_log.parquet for Kelly gate.
P4-3 | Story |  | ML regime classifier | WAVE 6 | Quant Lab | Kelly fraction activation and SOUL.md v3.0 update | Med | OPEN | 2 | wave-6,gate | Requires ≥30 trades in log. ✅ KELLY GATE.
▶ WAVE 7 — Data Foundry (Medallion Architecture / Databricks)
ARCH-1 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Data Foundry | Provision Databricks workspace and Unity Catalog — midas.bronze/silver/gold namespaces | Critical | OPEN | 3 | wave-7,gate | ✅ GATES ALL WAVE 7. midas catalog exists. ETL SP WRITE bronze. Claude MCP SP READ gold only.
ARCH-2
ARCH-3 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Data Foundry | Define temporal alignment standard — ISO-8601 UTC across all layers | High | OPEN | 2 | wave-7 | timestamp_normalise() utility. Documented in SYNC_CONTRACT v1.5. BLOCKED BY: ARCH-1.
BRNZ-1 | Story | MIDAS-133 | Bronze Layer | WAVE 7 | Data Foundry | Register ETL flat-file outputs as Delta Lake Bronze tables in Unity Catalog | High | OPEN | 5 | wave-7 | Immutable Bronze. BLOCKED BY: ARCH-1.
BRNZ-2 | Story | MIDAS-133 | Bronze Layer | WAVE 7 | Data Foundry | Add _rescued_data column handling for schema mismatches at Bronze ingest | High | OPEN | 3 | wave-7 | Schema drift to _rescued_data, not pipeline crash. BLOCKED BY: BRNZ-1.
BRNZ-3 | Story | MIDAS-133 | Bronze Layer | WAVE 7 | Data Foundry | Implement calculation hash (Gate 4) on Bronze model outputs | Critical | OPEN | 3 | wave-7 | SHA-256 hash of decision fields. CALC_DRIFT alert on divergence. BLOCKED BY: BRNZ-1.
SILV-1 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Data Foundry | Build Silver DLT pipeline — refined_market_prices streaming table | High | OPEN | 5 | wave-7 | BLOCKED BY: BRNZ-1, ARCH-2, ARCH-3.
SILV-2 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Data Foundry | Build Silver DLT pipeline — sovereign_stress_monitor streaming table | High | OPEN | 5 | wave-7 | BLOCKED BY: SILV-1.
SILV-3 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Data Foundry | Build Silver DLT pipeline — settlement_risk_indices streaming table | High | OPEN | 3 | wave-7 | BLOCKED BY: SILV-1.
SILV-4 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Data Foundry | Implement Great Expectations suite — 7 named expectations against ETL file types | High | OPEN | 8 | wave-7,gate | ✅ GATES GOLD LAYER. GX pass ≥99.5% required. BLOCKED BY: SILV-1.
GOLD-1 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Data Foundry | Build mkt_regime_final Gold materialized view — REGIME_RULES.md as code | High | OPEN | 5 | wave-7 | BLOCKED BY: SILV-4.
GOLD-2 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Data Foundry | Build risk_sentinel_status Gold materialized view — SOUL.md §3/§4 as code | High | OPEN | 5 | wave-7 | BLOCKED BY: SILV-4.
GOLD-3 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Data Foundry | Build liquidity_gate Gold materialized view — MACRO_TIERS §Tier -2 as code | Med | OPEN | 3 | wave-7 | BLOCKED BY: SILV-4.
GOLD-4 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Data Foundry | Build backtest_integrity Gold table — DAILY_STATE.md shadow journal as first-class asset | Med | OPEN | 3 | wave-7 | BLOCKED BY: SILV-4, P1-3.
GOLD-5 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Data Foundry | Build sync_audit Gold table — DEXTER_SYNC_CONTRACT.md compliance as code | Med | OPEN | 2 | wave-7 | BLOCKED BY: SILV-4.
MCP-1 | Story | MIDAS-133 | Claude MCP Integration | WAVE 7 | Data Foundry | Wire Claude MCP Databricks connector to Gold tables — read-only service principal | High | OPEN | 3 | wave-7,agent-integrated | Claude becomes auditor not calculator. BLOCKED BY: GOLD-1, GOLD-2.
MCP-2 | Story | MIDAS-133 | Claude MCP Integration | WAVE 7 | Data Foundry | Add Gold table query examples to Phase 0 and Phase 2 prompts in manifest | Med | OPEN | 2 | wave-7 | BLOCKED BY: MCP-1.
SYNC-4 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Data Foundry | Update SYNC_CONTRACT v1.5 — Medallion layer mapping and temporal alignment standard | Med | OPEN | 2 | wave-7 | BLOCKED BY: ARCH-3.
SYNC-5 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Data Foundry | Annotate existing Wave 2/3/6 items with Medallion layer equivalence notes | Low | OPEN | 1 | wave-7 | Maps AWAP→Gate1, Parquet→Bronze, Feast→Gold etc.
▶ WAVE 8 — Team 0: SE-Infra (Agentic Stack: TrustGraph / OpenClaw / OpenWolf / LMCache) ★ NEW
TGRAPH-1 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Provision TrustGraph instance — Docker Compose deployment on local/Azure node | High | OPEN | 3 | wave-8,trustgraph,new | BLOCKED BY: GOLD-1. Cannot ingest regime nodes before Gold table exists. docker compose up -d.
TGRAPH-2
TGRAPH-3 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Build Gold → TrustGraph export job — daily scheduled ingest from midas.gold.* | High | OPEN | 5 | wave-8,trustgraph,new | Scheduled post-Gold cron step. Exports regime_label, conviction_cap, sec_signals to graph nodes. BLOCKED BY: TGRAPH-1, GOLD-1, GOLD-2.
TGRAPH-4 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Ingest SOUL.md, REGIME_RULES.md, MACRO_TIERS.md as graph relationship edges | Med | OPEN | 5 | wave-8,trustgraph,new | Foundation docs become edges: [Rule]→[enforces]→[Regime]. Enables GraphRAG reasoning over policy. BLOCKED BY: TGRAPH-2.
TGRAPH-5 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Wire TrustGraph MCP server to OpenClaw config — context retrieval endpoint | Med | OPEN | 3 | wave-8,trustgraph,agent-integrated,new | Add @trustgraph-ai/mcp-server to OpenClaw MCP config. BLOCKED BY: TGRAPH-3.
TGRAPH-6 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Build Context Core export — midas.core package from Gold + foundation docs | Med | OPEN | 3 | wave-8,trustgraph,new | trustgraph core export midas-gold. Used by OpenClaw for zero-hallucination grounding. BLOCKED BY: TGRAPH-4.
TGRAPH-7 | [8 empty] | 2 | wave-8,trustgraph,new | Daily assertion: graph[regime_label] == gold.mkt_regime_final.regime_label. Fail → Slack alert.
OW-1 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Install and initialise OpenWolf (cytostack) in Dexter ETL repo — npm install -g openwolf && openwolf init | High | OPEN | 2 | wave-8,openwolf,new | Creates .wolf/ directory. Hooks fire on every Claude Code file operation. Immediate token reduction.
OW-2
OW-3
OW-4 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Set TTL policy for OpenWolf memory items — align with OB-4 30-day retention policy | Med | OPEN | 2 | wave-8,openwolf,new | Memory TTL prevents cerebrum.md bloat. Mount .wolf/ to persistent storage. BLOCKED BY: OB-4.
OC-1 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Containerise OpenClaw gateway — Docker image with env vars, no plaintext credentials | High | OPEN | 3 | wave-8,openclaw,new | docker run -p 18789:18789 andreaskasper/openclaw. CRON-2 (env vars) must be DONE first. BLOCKED BY: CRON-2.
OC-2 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Build MIDAS skill library v1.0 — get_regime_state, get_sec_signal, enforce_risk_policy, execute_trade_policy | High | OPEN | 5 | wave-8,openclaw,agent-integrated,new | Agent skills as executable contracts. Skills query Gold only — no recomputation. BLOCKED BY: MCP-1.
OC-3 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Wire OpenClaw skills to Gold tables — enforce read-only, no recomputation rule in skill definitions | High | OPEN | 5 | wave-8,openclaw,agent-integrated,new | Skill constraint: NEVER recompute conviction_cap or regime_label. Always SELECT from midas.gold.*. BLOCKED BY: OC-2, TGRAPH-5.
OC-4 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Build get_midas_consensus skill — deterministic fusion of regime + gamma + SEC signals | Med | OPEN | 3 | wave-8,openclaw,new | IF regime=VOL_EXPANSION AND gamma=EXPANSION AND sec=NEGATIVE → HIGH_CONFIDENCE_SHORT. Conviction 0-1. BLOCKED BY: OC-3.
OC-5 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Build execute_trade_policy skill — conviction gate + risk cap enforcement before any execution | Med | OPEN | 3 | wave-8,openclaw,new | If regime=BLOCKED OR conviction<0.6 → block trade. Log to midas.gold.trade_log. BLOCKED BY: OC-4, GOLD-2.
OC-6 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Wire OpenClaw to TrustGraph MCP for context retrieval during skill execution | Med | OPEN | 2 | wave-8,openclaw,trustgraph,new | OpenClaw calls TrustGraph for causal chain before trade. BLOCKED BY: TGRAPH-5, OC-3.
LMC-1 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Evaluate LMCache deployment — benchmark KV reuse for Phase 0-5 NEWS_CORPUS multi-turn sessions | Low | OPEN | 3 | wave-8,lmcache,new | Benchmark before deploying. LMCache only justified if NEWS_CORPUS re-processing cost exceeds caching overhead. BLOCKED BY: OC-1.
LMC-2 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Configure LMCache vLLM endpoint — docker pull lmcache/vllm-openai, integrate with OpenClaw inference | Low | OPEN | 3 | wave-8,lmcache,new | Only deploy if LMC-1 benchmark justifies. Point OpenClaw to lmcache endpoint. BLOCKED BY: LMC-1.
NET-1 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Provision Tailscale mesh — local node + Databricks + TrustGraph + OpenClaw VM private network | Med | OPEN | 2 | wave-8,infrastructure,new | Tailscale keeps stack private. No public ports. Colab test environment connects via Tailscale.
▶ GOVERNANCE — Assurance & Ops (ONGOING)
GOV-1 | Story | MIDAS-134 | Governance | GOVERNANCE | Assurance & Ops | Maintain DEXTER_SYNC_CONTRACT.md — canonical threshold + ticker registry | Med | ONGOING | 1 | governance | ONGOING. SYNC_CONTRACT is single source of truth.
GOV-2 | Story | MIDAS-134 | Governance | GOVERNANCE | Assurance & Ops | Foundation file versioning — SOUL/MACRO_TIERS/REGIME_RULES in sync with ETL | Med | ONGOING | 1 | governance | ONGOING. ETL MAJOR bump requires all three foundation files updated.
GOV-3 | Story | MIDAS-134 | Governance | GOVERNANCE | Assurance & Ops | NotebookLM corpus reload on MAJOR ETL version bumps | High | ONGOING | 1 | governance | ONGOING. MAJOR bump = Phase 0 prompt may break.
GOV-4 | Story | MIDAS-134 | Governance | GOVERNANCE | Assurance & Ops | Sync workflow enforcement — ETL TRIGGERS = canonical, foundation files = English | Med | ONGOING | 1 | governance | ONGOING. ETL first, then foundation files describe the value.
OC-5
LMC-1
LMC-2
TGRAPH-2 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Define MIDAS ontology schema — nodes: regime, asset, signal, filing, tier | High | OPEN | 5 | wave-8,trustgraph,new | BLOCKED BY: TGRAPH-1. AC: Schema published. Nodes: Regime, Asset, Signal, Filing, Tier. Edges: enforces, implies, blocks, caused_by.
TGRAPH-7 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Validate TrustGraph zero-hallucination: graph regime node must match midas.gold value | Low | OPEN | 2 | wave-8,trustgraph,new | BLOCKED BY: TGRAPH-3. AC: Daily assertion job. If graph[regime_label] != gold.regime_label → DRIFT alert to #dexter-alerts.
OW-2 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Populate cerebrum.md — encode SOUL.md guardrails as OpenWolf known-mistake rules | High | OPEN | 3 | wave-8,openwolf,new | BLOCKED BY: OW-1. AC: cerebrum.md contains rules: (1) Never recompute conviction_cap — read midas.gold. (2) All metric outputs include model_name suffix. (3) Do not query Bronze/Silver directly for decisions. Compliance ~85-90%.
OW-3 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Configure openwolf cron to mirror CRON-1 through CRON-8 for local dev/test | Med | OPEN | 2 | wave-8,openwolf,new | BLOCKED BY: OW-1. AC: openwolf cron list shows CRON-1 through CRON-8. openwolf cron run <id> executes step locally. Enables dev testing without Azure VM.
Total Stories: 119 ¦ Total Story Points: 363 ¦ + Fisher-Rao FIL epic: 8 stories, 39 pts (see Fisher-Rao sheet) ¦ GRAND TOTAL incl. FIL: 127 stories, 402 pts ¦ Wave 8 NEW (★): 20 stories, 64 pts ¦ v9 — 2026-04-01
▶ FISHER-RAO FIL EPIC (8 stories, 39 pts) — see 'Fisher-Rao FIL Import' sheet for full Jira import
FIL-1 (Fisher matrix, 8pt) ¦ FIL-2 (geom features, 5pt) ¦ FIL-3 (schema v1.1, 3pt) ¦ FIL-4 (gold view, 5pt) ¦ FIL-5 (TIER_AUDIT scores, 3pt) ¦ FIL-6 (HMM upgrade, 8pt) ¦ FIL-7 (STRUCTURE_SHIFT, 2pt) ¦ FIL-8 (feature pruning, 5pt)

## Jira Automation Rules
DEXTER / MIDAS — Jira Automation Rules (Team Topologies + PgMP Governance)
Rule # | Rule Name | Trigger Condition | Condition Detail | Action | Action Detail | Priority
── | TEAM ROUTING RULES
R-01 | Route to Sentinel Alpha | Epic Link IN list | SCRAPLING, GMISR_V2.0, SCORED_METRICS, ADVANCED_SIGNALS, MODEL_DELTA, POLYMARKET_LAYER, ECON_CALENDAR, EDGAR_V2.0 | Set 'Team' field | Sentinel Alpha | HIGH
R-02 | Route to Data Foundry | Epic Link IN list | IDEMPOTENCY, INFRASTRUCTURE, MEDALLION_ARCHITECTURE, BRONZE_LAYER, SILVER_LAYER, GOLD_LAYER, CLAUDE_MCP_INTEGRATION | Set 'Team' field | Data Foundry | HIGH
R-03 | Route to Assurance & Ops | Epic Link IN list | ETL_BUG_FIXES, DOCS, SECURITY, DEAD-LETTER_QUEUE, OFFLINE_OBSERVER, AWAP_PATTERN, SCHEMA_COMPAT, OBSERVABILITY, GOVERNANCE | Set 'Team' field | Assurance & Ops | HIGH
R-04 | Route to Quant Lab | Epic Link IN list | PARQUET_SNAPSHOT_LAYER, DUCKDB_ANALYTICS_LAYER, FEATURE_STORE, ML_REGIME_CLASSIFIER, TRACK_B_SHADOW | Set 'Team' field | Quant Lab | HIGH
── | GOVERNANCE & DRIFT RULES
R-05 | Calculation Drift Guard | Issue Created OR In-Progress | Epic Link = GOLD_LAYER OR summary contains 'metric' OR summary contains 'regime' | Edit Issue Description | APPEND: ⚠️ PRE-REQ: All metric outputs from this task must include model_name suffix (e.g. _CLAUDE_SONNET_4_6) to prevent calculation drift per 2026-02-25 audit protocol. | CRITICAL
R-06 | Agent-First Tag | Issue Created | Summary contains 'OpenClaw' OR summary contains 'Claude MCP' OR summary contains 'agentic' | Add Label + Set Priority | Add label: agent-integrated. Set priority: High. | HIGH
R-07 | Medallion Integrity Sub-task | Issue Transitioned → Done | Component = Databricks-Platform OR Databricks-SQL | Create Sub-task in Assurance & Ops | Create: 'Validate Schema Drift in Unity Catalog for [parent issue]'. Assign to Assurance & Ops. Priority: High. | HIGH
R-08 | GOV-2 Foundation File Sync | Issue Transitioned → Done | ID contains 'ETL' AND summary contains 'MAJOR' OR version bump 2.x.0.0 tag | Create sub-tasks | Create 3 governance sub-tasks: (1) Update SOUL.md version (2) Update MACRO_TIERS version (3) Update REGIME_RULES version. Link all to MIDAS-134 (Governance epic). | CRITICAL
── | PHASE GATE RULES
R-09 | Kelly Gate Circuit Breaker | Issue Transitioned → Done | ID = P4-1 (HMM Classifier) OR ID = P4-3 (Kelly activation) | Send Slack Alert | Post to #dexter-alerts: '⚠️ HUMAN CHECK REQUIRED: ML Model P4-1/P4-3 complete. Verify 30-trade shadow journal PHASE1_AGREEMENT >= 90% before promoting HMM weights to SOUL.md v3.0' | CRITICAL
R-10 | ARCH-1 Gate Enforcement | Epic Transitioned → In Progress | Epic Link IN (BRONZE_LAYER, SILVER_LAYER, GOLD_LAYER, CLAUDE_MCP_INTEGRATION) | Check Blocker | Block all Wave 7 stories with blocker link to ARCH-1 (Provision Databricks workspace). Do not allow In Progress unless ARCH-1 = DONE. | CRITICAL
R-11 | Wave Gate: Corpus before ML | Issue Created | Epic Link IN (PARQUET_SNAPSHOT_LAYER, ML_REGIME_CLASSIFIER) | Add Blocker Link | Auto-link as BLOCKED BY: AW-2 (AWAP audit), SC-2 (schema validation), ID-3 (atomic write). These Wave 2/3 items must be DONE. | HIGH
R-12 | GX Gate Enforcement | Issue Transitioned → In Progress | Epic Link = GOLD_LAYER | Check Blocker | Block Gold layer work with blocker to SILV-4 (Great Expectations suite). Gold should not be published until Silver GX suite passes at ≥99.5%. | HIGH
── | OBSERVABILITY RULES
R-13 | SLA Miss Alert | Scheduled daily | OB-1 (SLA Monitor) active: ETL run total > 20 minutes | Send Slack Alert | Post to #dexter-alerts: CRITICAL SLA MISS — ETL runtime exceeded 20min threshold. Tag Assurance & Ops lead. | CRITICAL
R-14 | Unclassified News Alert | Scheduled (weekly audit) | OB-3 (Filter Interceptor): any feed > 40% UNCLASSIFIED for 3 consecutive runs | Create Jira Issue | Auto-create Issue: 'FEED QUALITY DEGRADED: [feed name] at [X]% unclassified'. Assign to Assurance & Ops, Priority: Medium. | MEDIUM
R-15 | Complex Subsystem Alert | Issue Created OR Estimated | Team = Quant Lab AND Story Points > 5 | Add Comment | Auto-comment: '🧠 HIGH-COMPLEXITY ML TASK: Ensure OpenClaw has been used to draft initial pseudocode before manual dev begins. Consider pair-programming with Sentinel Alpha for signal validation.' | MEDIUM
── FISHER-RAO LAYER AUTOMATION RULES (FIL epic, added 2026-03-31)
R-16 | Geometry HMM Obs Upgrade Guard | Issue → In Progress | ID = FIL-6 | Check Blocker | Verify FIL-8 (feature pruning) = DONE AND FIL-3 (schema v1.1) = DONE AND P3-1 (Feast) = DONE before allowing FIL-6 In Progress. Stale features must not enter geometry HMM. | CRITICAL
R-17 | STRUCTURE_SHIFT Slack Gate | Scheduled daily (post-ETL) | FIL-7 active AND eigenvector_alignment < 0.85 for 2 runs | Send Slack Alert | Post to #dexter-alerts: STRUCTURE_SHIFT detected — Fisher eigenvector_alignment={val:.3f} for 2d. Factor rotation underway. Reduce directional exposure. Review Phase 2 GatePass. | HIGH
R-18 | Fisher Pruning Must Precede HMM | Issue Created | ID = FIL-6 created AND FIL-8 Status != DONE | Add Blocker Link | Auto-link: FIL-6 BLOCKED BY FIL-8. Feature collinearity audit must complete before HMM observation vector is finalised. | HIGH
R-19 | Fisher Conviction Cap Audit | Issue → Done | ID = FIL-4 (fisher_regime_engine gold view) | Create Sub-task in Assurance & Ops | Create: 'Validate fisher_conviction_multiplier range [0.2–1.0] in midas.gold.fisher_regime_engine'. Verify SOUL.md 0.4 floor preserved. Priority: Critical. | CRITICAL
R-20 | FIL Epic Wave Routing | Issue Created | Epic Link = FIL OR label = fisher-rao | Set Team field by wave | WAVE 5 → Assurance & Ops (FIL-7). WAVE 6 → Quant Lab (FIL-1/2/3/5/6/8). WAVE 7 → Data Foundry (FIL-4). Add label: fisher-rao. | HIGH
── | TEAM 0: SE-INFRA ROUTING RULES (added 2026-04-01)
R-00 | Route to Team 0: SE-Infra | Epic Link or ID matches | CRON-1,CRON-2,CRON-3,CRON-4,CRON-5,CRON-6,CRON-7,CRON-8, TGRAPH-1 to TGRAPH-7, OW-1 to OW-4, OC-1 to OC-6, LMC-1, LMC-2, NET-1, OR Epic Link = MIDAS-200 (Agentic Infra Stack) | Set 'Team' field | Team 0: SE-Infra | CRITICAL
── | WAVE 8 GATE RULES (added 2026-04-01)
R-21 | TrustGraph Gate: Gold must exist first | Issue → In Progress | ID starts with TGRAPH- | Check Blocker | Block TGRAPH-1 unless GOLD-1 = DONE. TrustGraph cannot ingest regime nodes that do not exist in Gold. | CRITICAL
R-22 | OpenClaw Gate: CRON-2 env vars before container | Issue → In Progress | ID = OC-1 (containerise OpenClaw) | Check Blocker | Block OC-1 unless CRON-2 = DONE. No plaintext credentials before containerisation. | CRITICAL
R-23 | LMCache benchmark gate | Issue → In Progress | ID = LMC-2 (configure LMCache endpoint) | Check Blocker + Comment | Block LMC-2 unless LMC-1 = DONE AND LMC-1 acceptance criteria (>30% token reduction) confirmed. LMCache is optional — only deploy if benchmark justifies. | HIGH
R-24 | OpenWolf cerebrum.md SOUL sync | Issue → Done | ID = GOLD-2 (risk_sentinel_status) OR ID = GOLD-1 (mkt_regime_final) | Create Sub-task in Team 0 | Create: 'Update cerebrum.md rule: confirm Gold table name matches production — do not recompute [regime/conviction].' Assign Team 0: SE-Infra. | HIGH
R-25 | TrustGraph drift validation daily trigger | Scheduled daily (post-ETL cron) | TGRAPH-7 active AND graph[regime_label] != midas.gold.mkt_regime_final.regime_label | Send Slack Alert | Post to #dexter-alerts: ⚠️ TRUSTGRAPH DRIFT — graph regime_label does not match Gold table. Possible stale graph ingest. Re-run TGRAPH-3 export job. | CRITICAL
R-26 | Route Wave 7 to Data Foundry (corrected from Sentinel Alpha) | Issue Created | Epic Link = MIDAS-133 OR Wave = WAVE 7 | Set 'Team' field | Data Foundry. NOTE: Wave 7 was previously (incorrectly) assigned to Sentinel Alpha in v8. All ARCH-*, BRNZ-*, SILV-*, GOLD-*, MCP-*, SYNC-4, SYNC-5 belong to Data Foundry. | CRITICAL

## Risk Register (PgMP)
DEXTER / MIDAS — Program Risk Register (PgMP Standard)
Risk ID | Category | Risk Title | Description | Probability | Impact | Risk Score | Mitigation Strategy | WBS Owner (Story) | Team Owner
── | DATA INTEGRITY RISKS
R-DI-01 | Data Integrity | FRED API Silent Failure | FRED/SOFR returns stale or zero values. System proceeds without detecting corruption, poisoning the TIER_AUDIT and Gold layer regime outputs. | Medium | Critical | 🔴 HIGH | DL-3 (Dead-Letter + FAILED.json), OO-2 (Offline Observer), SILV-4 (GX expectation: price > 0, WALCL IS NOT NULL). CONVICTION_CAP reduced 0.2 per critical failure (floor 0.2). | DL-3, OO-1, OO-2 | Assurance & Ops
R-DI-02 | Data Integrity | Calculation Drift (Model Divergence) | Gemini and Claude lineages compute different regime labels or conviction caps from identical Silver inputs. No mechanism detects the drift until operator notices discrepancy. | High | High | 🔴 CRITICAL | BRNZ-3 (SHA-256 hash of decision fields at Bronze write). CALC_DRIFT alert when hash diverges for same run_date. All metric files must include model_name suffix (e.g. _CLAUDE_SONNET_4_6). | BRNZ-3 | Assurance & Ops
R-DI-03 | Data Integrity | Schema Evolution Breaking Downstream | New optional field added to ETL output breaks Silver DLT pipeline or GX expectations. Forward-compatible change treated as backward-incompatible. | Medium | High | 🟠 HIGH | SC-1 (schema registry), SC-2 (validate_schema with 3-tier: compatible / forward-compat / incompatible), SC-3 (SCHEMA_DRIFT report). BRNZ-2 (_rescued_data column). 3-run auto-learn for optional fields. | SC-1, SC-2, SC-3 | Assurance & Ops
── | OPERATIONAL RISKS
R-OP-01 | Operational | Cron UTC Offset | Cron fires at 01:45 ET instead of 05:45 ET (CRON-1 unfixed). ETL runs on yesterday's stale data. GMISR delivered before pre-market liquidity surge window. | High | High | 🔴 CRITICAL | CRON-1: fix cron to 10 45 * * 1-5 UTC. CRON-8: restrict to weekdays. This is currently the highest-urgency infrastructure item — affects every downstream wave. | CRON-1, CRON-8 | Assurance & Ops
R-OP-02 | Operational | API Key Exposure | FINNHUB_KEY, FRED_API_KEY, SLACK_WEBHOOK in plaintext in cron prompt body. Anyone with cron access has all credentials. Security breach risk. | Medium | Critical | 🔴 CRITICAL | CRON-2: migrate all keys to Azure VM environment variables or Key Vault. CRON-3: remove SLACK_WEBHOOK from prompt body to prevent double-fire. | CRON-2, CRON-3 | Assurance & Ops
R-OP-03 | Operational | Local Node Single Point of Failure | System runs on local K3s cluster / Linux machine. Hardware failure eliminates ETL output, NotebookLM corpus, and Parquet store with no failover. | Medium | High | 🟠 HIGH | OB-1 (SLA monitoring < 10min WARNING, <20min CRITICAL). OB-4 (30-day TTL + TIER_AUDIT indefinite retention). Wave 7 Databricks migration eliminates this risk entirely. | OB-1, OB-4, ARCH-1 | Assurance & Ops
── | MODELING RISKS
R-ML-01 | Modeling | HMM Premature Activation | Regime classifier (P4-1) activated before 30-trade Kelly gate passes. Model trained on insufficient labelled data. False regime signals trigger incorrect conviction caps. | Low | Critical | 🟠 HIGH | P4-3: hard gate — Kelly fraction requires >= 30 closed trade_log entries. Jira R-09 automation blocks P4-1 transition to Done without human sign-off. Fixed-fractional (1%) active until gate. | P4-1, P4-3 | Quant Lab
R-ML-02 | Modeling | Shadow Journal Drift (Epistemic Accuracy) | PHASE1_AGREEMENT (human vs model) drops below 60% for 30-day rolling window. Operator intuition diverging from system signals. Trades may be sized incorrectly. | Medium | High | 🟠 HIGH | GOLD-4 (backtest_integrity table). Rolling epistemic_accuracy computed from DAILY_STATE.md. Slack alert if < 60%. Phase 10 weekly audit reviews per-model agreement score. | GOLD-4 | Quant Lab
── | ARCHITECTURE RISKS
R-AR-01 | Architecture | ARCH-1 Blocking All Wave 7 | Unity Catalog provisioning (ARCH-1) is the absolute prerequisite for all Bronze/Silver/Gold/MCP work. Any delay cascades to all Wave 7 items simultaneously. | Medium | Critical | 🔴 CRITICAL | ARCH-1 first in Wave 7 sprint. Jira R-10 auto-blocks all Wave 7 stories until ARCH-1 = DONE. Databricks already connected (dbc-0df8fb6d-4908.cloud.databricks.com) — provisioning risk lower than greenfield. | ARCH-1 | Data Foundry
R-AR-02 | Architecture | Epic 21 Dual-Layer Duplication | Wave 2 (AWAP / local) and Wave 7 (DLT / cloud) implement similar Bronze→Silver logic independently, causing divergent results and wasted engineering effort. | Medium | High | 🟠 HIGH | SYNC-5 (annotation): Wave 2/3/6 items explicitly annotated as local equivalents of Medallion layers. SYNC-4 (v1.5 contract) defines which layer supersedes. Architecture review gate before Wave 7 sprint starts. | SYNC-5, SYNC-4 | Data Foundry
── FISHER-RAO MODELING RISKS (FIL epic, added 2026-03-31)
R-ML-03 | Modeling | Static Fisher Averaging Destroys Signal | Fisher matrix computed over full Parquet history instead of rolling windows. March 2026 VOL_EXPANSION geometry averaged with January RISK_ON → meaningless tensor. | Medium | High | HIGH | FIL-1: rolling windows only (20d default). VOLATILITY_WATCH_FLAG active → 5d window. Window length governed by VX1/VX2 ratio threshold in SOUL.md. | FIL-1 | Quant Lab
R-ML-04 | Modeling | Silent Eigenvector Rotation — Regime Label Unchanged, Structure Changed | Regime label stays B but Fisher eigenvectors rotate 30°+. Signal the system is trading has fundamentally changed direction with no alert fired. | Medium | High | HIGH | FIL-7: STRUCTURE_SHIFT alert when alignment < 0.85 for 2 consecutive days. Fires regardless of regime label change. Jira R-17 triggers Slack. | FIL-7 | Assurance & Ops
R-ML-05 | Modeling | Small-Eigenvalue Overfitting (NDI/HDS as False Dimensions) | NDI and HDS produce small but non-zero Fisher eigenvalues — appear as new dimensions but are noise fitted to 30 Shadow Journal labels. Inflates effective rank. | Medium | Medium | MEDIUM | FIL-8: 10%-of-lambda1 threshold filter. Off-diagonal collinearity collapses HDS to NLLI. NDI likely removed from HMM input. Documents in SOUL.md §3.2. | FIL-8 | Quant Lab
R-ML-06 | Modeling | High Fisher Info + Low Executability = False Alpha | Polymarket or EDGAR forensic signals show high Fisher information but require 1-2d signal-to-trade lag or illiquid derivatives. System over-weights in conviction. | Low | High | MEDIUM | FIL-5: EXECUTABILITY_FLAG per source. ALPHA_SCORE = Fisher_info × executability_weight. Only ALPHA_SCORE > 0.5 eligible for HMM. Implements doc: 'Information × Executability'. | FIL-5 | Quant Lab

## Program Roadmap
DEXTER / MIDAS — Program Roadmap 2026-2027 (PgMP Phase-Gate Model)
Phase | Milestone | Wave(s) | Target Quarter | Epics in Scope | Key Gate | North Star Contribution | Status | Pts
Phase 1 Hardened Foundations | M0 — Infrastructure Stable | WAVE 0 | Q1 2026 (Mar) | ETL Bug Fixes, Docs, Infrastructure, Security | Cron fires at 05:45 ET daily. API keys in env vars. No duplicate Slack fire. | Punctuality: Structural prerequisite for all downstream waves. | IN PROGRESS | 29
Phase 1 Hardened Foundations | M1 — Error Visibility | WAVE 1 | Q2 2026 (Apr-May) | Dead-Letter Queue (DL-1 to DL-3), Offline Observer (OO-1 to OO-3) | FAILED_{date}.json written on every run. CONVICTION_CAP auto-reduced on critical failures. OO-2 observer live. | Data Integrity: Eliminates silent failures that would poison Gold layer regime outputs. | TO DO | 20
Phase 1 Hardened Foundations | M2 — Quality Gates | WAVE 2 | Q2 2026 (May-Jun) | AWAP Pattern (AW-1 to AW-4), Schema Compat (SC-1 to SC-3) | All modules pass pre/post-write audit. SCHEMA_DRIFT auto-detected. No malformed data in staging. | Data Integrity: Local equivalent of Medallion Gate 1/2. Prevents garbage-in to GMISR. | TO DO | 27
Phase 1 Hardened Foundations | M3 — Idempotency Gate | WAVE 3 | Q3 2026 (Jul) | Idempotency (ID-1 to ID-6) | --force-rerun on any date T-1 to T-5 produces binary-identical MANIFEST.json and TIER_AUDIT. | Reliability: Enables deterministic re-runs and audit trail. Local equivalent of Delta Lake ACID. | TO DO | 21
Phase 2 Corpus Intelligence | M4 — Corpus Enrichment | WAVE 4 | Q3 2026 (Aug-Sep) | Scrapling (SCRAP-1 to SCRAP-4) | Category A global sources (BoJ, PBOC, BoE, BCB, RBI) integrated into NEWS_CORPUS. SYNC_CONTRACT v1.4. | Breadth: Brief covers non-Western macro. NLLI velocity scoring across enriched corpus. | TO DO | 9
Phase 2 Corpus Intelligence | M5 — Alpha Signals | WAVE 5 | Q4 2026 (Oct-Nov) | GMISR v2.0, Scored Metrics (HDS/VPI/LFI/NLLI/PSI/CXOD), Model Delta, Econ Calendar, EDGAR v2.0, Polymarket | All 7 scored metrics live in TIER_AUDIT. GMISR Phase 5 includes Blocks 2.5, 2.7, 5, 10, 11. | Accuracy: System produces scored signals not raw text. Closes narrative-to-price arbitrage gap. | TO DO | 101
Phase 2 Corpus Intelligence | M6 — ML Readiness | WAVE 6 | Q4 2026 (Dec) | Parquet snapshot layer, DuckDB, Feature Store (Feast), HMM Classifier, Observability ¦ FIL-6 geometry-HMM upgrade required. FIL-8 feature pruning gates FIL-6. | Kelly Activation Gate: 30 closed trades in trade_log.parquet. HMM P4-1 accuracy >= 90% vs shadow journal. | Automation: Regime label sourced from model, not human. Circuit breaker = epistemic_accuracy < 60%. | TO DO | 115
Phase 3 Autonomous Orchestration | M7 — Medallion Architecture | WAVE 7 | Q1 2027 (Jan-Mar) | Databricks Unity Catalog, Bronze/Silver/Gold DLT, Great Expectations, Claude MCP Integration | ARCH-1 complete. midas.gold.* tables live. Claude queries Gold not text files. Calculation drift = 0. | Determinism: Single source of truth. All consumers (Claude, OpenClaw, dashboards) read same Gold table. | TO DO | 80
Phase 3 Autonomous Orchestration | M8 — Autonomous GMISR (North Star) | WAVE 8 | Q2 2027 | All waves integrated. OpenClaw cron fully autonomous. | 10 consecutive days: Slack ≤ 06:35 ET, PHASE1_AGREEMENT ≥ 90%, CRITICAL_FAILURES = 0, Cost ≤ $2.50/day. | ✅ NORTH STAR: Fully agentic daily macro brief. Human role = auditor only (circuit breaker). | PLANNED | 0
Phase 4 Agentic Infra | M8a — Agent Stack Deployed ★ NEW | WAVE 8 | Q2-Q3 2027 | Team 0: SE-Infra ¦ TrustGraph (TGRAPH-1→7, 26 pts) ¦ OpenWolf (OW-1→4, 9 pts) ¦ OpenClaw MIDAS Skills (OC-1→6, 21 pts) ¦ LMCache eval (LMC-1→2, 6 pts) ¦ Tailscale (NET-1, 2 pts) | GOLD-1 done → TGRAPH-1 starts. CRON-2 done → OC-1 starts. LMC-1 benchmark pass → LMC-2. All 20 stories DONE. TGRAPH-7 daily assertion passing. | North Star enabler: OpenClaw queries Gold via skills. TrustGraph provides causal reasoning. OpenWolf prevents dev-time drift. Full agentic stack ready for autonomous GMISR. | TO DO | 64

## JQL Filters & Team Boards
DEXTER / MIDAS — JQL Filters for Team Topology Boards (Jira)
Team (Topology) | Board Name | JQL Query | Purpose | Refresh
Sentinel Alpha | Alpha Stream Board | "Epic Link" IN (SCRAPLING, GMISR_V2.0, SCORED_METRICS, ADVANCED_SIGNALS, MODEL_DELTA, POLYMARKET_LAYER, ECON_CALENDAR, EDGAR_V2.0) OR "Epic Name" ~ "Scrapling" OR "Epic Name" ~ "GMISR" ORDER BY priority DESC | Direct alpha generation: news enrichment, scored metrics, GMISR synthesis, agentic workflows. | Daily
Data Foundry | Data Platform Board | "Epic Link" IN (IDEMPOTENCY, INFRASTRUCTURE, MEDALLION_ARCHITECTURE, BRONZE_LAYER, SILVER_LAYER, GOLD_LAYER, CLAUDE_MCP_INTEGRATION) OR summary ~ "Databricks" OR summary ~ "Unity Catalog" OR summary ~ "Delta Lake" ORDER BY priority DESC | Medallion architecture, DLT pipelines, Gold materialized views, Claude MCP wiring. | Daily
Assurance & Ops | Quality & Governance Board | "Epic Link" IN (ETL_BUG_FIXES, DOCS, SECURITY, DEAD-LETTER_QUEUE, OFFLINE_OBSERVER, AWAP_PATTERN, SCHEMA_COMPAT, OBSERVABILITY, GOVERNANCE) OR labels = "governance" ORDER BY priority DESC | Error visibility, quality gates, cron stability, schema compat, SYNC_CONTRACT governance. | Daily
Quant Lab | ML & Analytics Board | "Epic Link" IN (PARQUET_SNAPSHOT_LAYER, DUCKDB_ANALYTICS_LAYER, FEATURE_STORE, ML_REGIME_CLASSIFIER, TRACK_B_SHADOW) OR summary ~ "HMM" OR summary ~ "hmmlearn" OR summary ~ "Kelly" ORDER BY priority DESC | Parquet schema, DuckDB dashboards, Feast feature store, HMM regime classifier, shadow pipeline. | Sprint
All Teams (Program) | North Star Dashboard | project = "MIDAS" AND (labels = "agent-integrated" OR summary ~ "06:35" OR summary ~ "Kelly" OR summary ~ "CONVICTION_CAP" OR summary ~ "Gold" OR labels = "governance") ORDER BY priority DESC | Cross-team view of items directly contributing to the Autonomous GMISR North Star (M8). | Weekly
All Teams (Program) | Critical Gates View | project = "MIDAS" AND (id IN (CRON-1, CRON-2, ARCH-1, DL-3, SC-2, ID-3, SILV-4, GOLD-1, MCP-1, P4-3) OR labels = "gate" OR priority = Critical) ORDER BY priority DESC, created ASC | Program phase-gate blockers only. Items that block the next wave from starting. | Daily
Assurance & Ops | Calculation Drift Monitor | project = "MIDAS" AND (labels = "calculation-drift" OR summary ~ "hash" OR summary ~ "model_name" OR summary ~ "BRNZ-3" OR id = "GOLD-4") ORDER BY updated DESC | All items related to the model-name suffix and calculation drift detection protocol. | Weekly
Fisher-Rao Layer | Fisher Geometry Board | "Epic Link" = FIL OR labels = "fisher-rao" OR id IN (FIL-1,FIL-2,FIL-3,FIL-4,FIL-5,FIL-6,FIL-7,FIL-8) ORDER BY priority DESC, created ASC | Rolling Fisher matrix, eigenvalue dynamics, geometry-HMM upgrade (updates P4-1), feature pruning (audits SCORE-1/4, GMISR-6), STRUCTURE_SHIFT alerting. | Sprint
Team 0: SE-Infra | SE Infrastructure Board | "Epic Link" = MIDAS-200 OR id IN (CRON-1,CRON-2,CRON-3,CRON-4,CRON-5,CRON-6,CRON-7,CRON-8) OR labels IN ("wave-8","openwolf","trustgraph","openclaw","lmcache","new") OR summary ~ "TrustGraph" OR summary ~ "OpenWolf" OR summary ~ "LMCache" OR summary ~ "Tailscale" OR summary ~ "cerebrum" ORDER BY priority DESC | Team 0 owner board: Wave 0 cron/security fixes + Wave 8 full agentic stack. TrustGraph, OpenWolf, OpenClaw containerisation, LMCache, Tailscale network. | Daily
Data Foundry (corrected) | Data Platform Board (v2) | "Epic Link" IN (IDEMPOTENCY, MIDAS-133, MEDALLION_ARCHITECTURE, BRONZE_LAYER, SILVER_LAYER, GOLD_LAYER, CLAUDE_MCP_INTEGRATION) OR summary ~ "Databricks" OR summary ~ "Unity Catalog" OR summary ~ "Delta Lake" OR id IN (ARCH-1,ARCH-2,ARCH-3,BRNZ-1,BRNZ-2,BRNZ-3,SILV-1,SILV-2,SILV-3,SILV-4,GOLD-1,GOLD-2,GOLD-3,GOLD-4,GOLD-5,MCP-1,MCP-2,SYNC-4,SYNC-5) ORDER BY priority DESC | CORRECTED v2: All Wave 7 Medallion stories now correctly routed to Data Foundry (were Sentinel Alpha in v8 topology). 19 stories, 61 pts. | Daily

## Wave 7 Jira Import
DEXTER / MIDAS — Wave 7 Jira Import: Medallion Architecture (Databricks) ¦ Team corrected: ALL Wave 7 → Data Foundry (was Sentinel Alpha) ¦ 2026-04-01
Issue ID | Issue Type | Epic Link | Epic Name | Wave | Team | Summary | Priority | Status | Story Pts | Acceptance Criteria (Key)
ARCH-1 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Data Foundry | Provision Databricks workspace and Unity Catalog — midas.bronze/silver/gold namespaces | Critical | OPEN | 3 | midas catalog exists. bronze/silver/gold schemas created. ETL SP has WRITE on bronze. Claude MCP SP has READ on gold only. ✅ BLOCKS all other Wave 7 items.
ARCH-2 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Data Foundry | Define canonical entity resolution schema — ticker normalisation map | High | OPEN | 3 | ENTITY_MAP table in Unity Catalog. GC=F→COM_GOLD, DX-Y.NYB→FX_DXY mapped. All Silver tables join through ENTITY_MAP. Calculation difference problem resolved.
ARCH-3 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Data Foundry | Define temporal alignment standard — ISO-8601 UTC across all layers | High | OPEN | 2 | timestamp_normalise() utility. All ingested timestamps → ingest_timestamp_utc. Documented in SYNC_CONTRACT v1.5.
BRNZ-1 | Story | MIDAS-133 | Bronze Layer | WAVE 7 | Data Foundry | Register ETL flat-file outputs as Delta Lake Bronze tables in Unity Catalog | High | OPEN | 5 | 9 Bronze tables: fred_summary, market_data, treasury_auctions, dollar_decomp, sec_ftd, edgar_filings, news_corpus, econ_calendar, polymarket_signals. Append-only. Lineage via _metadata.file_path.
BRNZ-2 | Story | MIDAS-133 | Bronze Layer | WAVE 7 | Data Foundry | Add _rescued_data column handling for schema mismatches at Bronze ingest | Medium | OPEN | 3 | DLT routes mismatched fields to _rescued_data. Daily Slack alert if rescued_count > 0 on critical tables. Equivalent of local SC-3 SCHEMA_DRIFT report.
BRNZ-3 | Story | MIDAS-133 | Bronze Layer | WAVE 7 | Data Foundry | Implement calculation hash (Gate 4) on Bronze model outputs | Critical | OPEN | 3 | SHA-256 hash of (regime_label, conviction_cap, dollar_composite) at Bronze write. CALCULATION_DRIFT Slack alert on hash divergence. Solves Gemini vs Claude model output drift.
SILV-1 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Data Foundry | Build Silver DLT pipeline — refined_market_prices streaming table | High | OPEN | 5 | 3 gates enforced. EXPECT (price > 0), EXPECT (ABS(brent-wti) < 15). Entity map join. midas.silver.refined_market_prices with source_origin lineage.
SILV-2 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Data Foundry | Build Silver DLT pipeline — sovereign_stress_monitor streaming table | High | OPEN | 5 | DOLLAR_DECOMP 4-layer completeness check. All 4 layers non-null before day marked COMPLETE. QUARANTINE for fra_ois anomalies.
SILV-3 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Data Foundry | Build Silver DLT pipeline — settlement_risk_indices streaming table | High | OPEN | 3 | SEC_FTD zero-price rows handled (newly listed securities). EDGAR entity names normalised via ENTITY_MAP. TQQQ_FTD as first-class column.
SILV-4 | Story | MIDAS-133 | Silver Layer | WAVE 7 | Data Foundry | Implement Great Expectations suite — 7 named expectations against ETL file types | High | OPEN | 8 | 7 named expectations active. GX Data Docs generated daily. All Silver tables have active GX suite. Failed rows logged + traceable. ≥99.5% pass rate. ✅ GATES all Gold layer work.
GOLD-1 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Data Foundry | Build mkt_regime_final Gold materialized view — REGIME_RULES.md as code | High | OPEN | 5 | Regime A/B/C SQL logic matches REGIME_RULES.md exactly. Gate 5 quorum: all critical Silver sources COMPLETE for date. Low_Confidence flag when stale. Reproducible from Silver inputs.
GOLD-2 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Data Foundry | Build risk_sentinel_status Gold materialized view — SOUL.md §3/§4 as code | High | OPEN | 5 | CONVICTION_CAP graduated logic: 1.0→0.5→0.4→0.0. RISK_SENTINEL_TRIGGER conditions match SOUL.md §4. Claude MCP queries this instead of TIER_AUDIT text.
GOLD-3 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Data Foundry | Build liquidity_gate Gold materialized view — MACRO_TIERS §Tier -2 as code | High | OPEN | 3 | net_liq_b = WALCL - TGA - RRP. is_blocked BOOL. gate_status OPEN/RESTRICTED/CLOSED. max_positions per regime. Phase 2 GatePass reads this directly.
GOLD-4 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Data Foundry | Build backtest_integrity Gold table — DAILY_STATE.md shadow journal as first-class asset | High | OPEN | 3 | Rolling epistemic_accuracy (30-day). Slack alert if < 60%. Feeds HMM training as label source. Primary ML feedback loop for regime classifier validation.
GOLD-5 | Story | MIDAS-133 | Gold Layer | WAVE 7 | Data Foundry | Build sync_audit Gold table — DEXTER_SYNC_CONTRACT.md compliance as code | Medium | OPEN | 2 | Daily diff of ETL TRIGGERS dict vs SOUL §3 canonical thresholds. SYNC_VIOLATION rows written on any drift. Replaces manual SYNC_CONTRACT audit.
MCP-1 | Story | MIDAS-133 | Claude MCP Integration | WAVE 7 | Data Foundry | Wire Claude MCP Databricks connector to Gold tables — read-only service principal | High | OPEN | 3 | Claude queries midas.gold.* via MCP. Claude does NOT compute regime — queries mkt_regime_final. Calculation differences between Gemini and Claude lineages eliminated.
MCP-2 | Story | MIDAS-133 | Claude MCP Integration | WAVE 7 | Data Foundry | Add Gold table query examples to Phase 0 and Phase 2 prompts in manifest | Medium | OPEN | 2 | MIDAS_SENTINEL_PROMPT_LIBRARY v2026.5. Gold table takes precedence over TIER_AUDIT text when both available. TIER_AUDIT remains fallback when MCP unavailable.
SYNC-4 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Data Foundry | Update SYNC_CONTRACT v1.5 — Medallion layer mapping and temporal alignment standard | High | OPEN | 2 | Medallion section added. Gold supersedes text files when available. Temporal alignment: ISO-8601 UTC. Wave/item cross-reference table included.
SYNC-5 | Story | MIDAS-133 | Medallion Architecture | WAVE 7 | Data Foundry | Annotate existing Wave 2/3/6 items with Medallion layer equivalence notes | Low | OPEN | 1 | AW-1/2/3/4 annotated as local Bronze→Silver Gate equivalents. Prevents dual-implementation of same logic in local and cloud layers.
Wave 7 Total Stories: 19

## Wave 8 Jira Import
DEXTER / MIDAS — Wave 8 Jira Import: Agentic Infra Stack ★ NEW 2026-04-01
Phase 3: TrustGraph (TGRAPH-1→7, 26 pts) ¦ Phase 4: OpenClaw + OpenWolf + LMCache + Network (OW-1→4, OC-1→6, LMC-1→2, NET-1, 38 pts) ¦ Owner: Team 0 — SE-Infra ¦ Gate: GOLD-1 must be DONE before TGRAPH-1 starts ¦ CRON-2 must be DONE before OC-1 starts
Issue ID | Issue Type | Epic Link | Epic Name | Wave | Team | Summary | Priority | Status | Story Pts | Labels | Acceptance Criteria / Blocked By
── Phase 3: TrustGraph — Knowledge Graph Layer (BLOCKED BY: GOLD-1)
TGRAPH-1 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Provision TrustGraph instance — Docker Compose deployment on local/Azure node | High | OPEN | 3 | wave-8,trustgraph,new | BLOCKED BY: GOLD-1. docker compose up -d from TrustGraph repo. AC: TrustGraph API reachable at localhost:8000. Graph DB running.
TGRAPH-2 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Define MIDAS ontology schema — nodes: regime, asset, signal, filing, tier | High | OPEN | 5 | wave-8,trustgraph,new | BLOCKED BY: TGRAPH-1. AC: Schema published. Nodes: Regime, Asset, Signal, Filing, Tier. Edges: enforces, implies, blocks, caused_by.
TGRAPH-3 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Build Gold → TrustGraph export job — daily scheduled ingest from midas.gold.* | High | OPEN | 5 | wave-8,trustgraph,new | BLOCKED BY: TGRAPH-1, GOLD-1, GOLD-2. AC: Cron exports regime_label, conviction_cap, sec_signals as graph nodes. Runs after Gold tables update.
TGRAPH-4 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Ingest SOUL.md, REGIME_RULES.md, MACRO_TIERS.md as graph relationship edges | Med | OPEN | 5 | wave-8,trustgraph,new | BLOCKED BY: TGRAPH-2. AC: Foundation docs parsed. [Rule]→[enforces]→[Regime] edges exist. GraphRAG can trace conviction cap to SOUL §3 rule.
TGRAPH-5 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Wire TrustGraph MCP server to OpenClaw config — context retrieval endpoint | Med | OPEN | 3 | wave-8,trustgraph,agent-integrated,new | BLOCKED BY: TGRAPH-3. AC: @trustgraph-ai/mcp-server in OpenClaw config. OpenClaw can retrieve regime causal chain via MCP call.
TGRAPH-6 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Build Context Core export — midas.core package from Gold + foundation docs | Med | OPEN | 3 | wave-8,trustgraph,new | BLOCKED BY: TGRAPH-4. AC: trustgraph core export midas-gold produces midas.core. OpenClaw loads core on startup. Zero-hallucination grounding active.
TGRAPH-7 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Validate TrustGraph zero-hallucination: graph regime node must match midas.gold value | Low | OPEN | 2 | wave-8,trustgraph,new | BLOCKED BY: TGRAPH-3. AC: Daily assertion job. If graph[regime_label] != gold.regime_label → DRIFT alert to #dexter-alerts.
── Phase 4a: OpenWolf — Dev-time Memory & Token Governance (Team 0: SE-Infra)
OW-1 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Install and initialise OpenWolf (cytostack) in Dexter ETL repo | High | OPEN | 2 | wave-8,openwolf,new | npm install -g openwolf && openwolf init in dexter/ repo root. AC: .wolf/ directory created. openwolf status shows active hooks. Token ledger running.
OW-2 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Populate cerebrum.md — encode SOUL.md guardrails as OpenWolf known-mistake rules | High | OPEN | 3 | wave-8,openwolf,new | BLOCKED BY: OW-1. AC: cerebrum.md contains rules: (1) Never recompute conviction_cap — read midas.gold. (2) All metric outputs include model_name suffix. (3) Do not query Bronze/Silver directly for decisions. Compliance ~85-90%.
OW-3 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Configure openwolf cron to mirror CRON-1 through CRON-8 for local dev/test | Med | OPEN | 2 | wave-8,openwolf,new | BLOCKED BY: OW-1. AC: openwolf cron list shows CRON-1 through CRON-8. openwolf cron run <id> executes step locally. Enables dev testing without Azure VM.
OW-4 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Set TTL policy for OpenWolf memory items — align with OB-4 30-day retention | Med | OPEN | 2 | wave-8,openwolf,new | BLOCKED BY: OW-1, OB-4. AC: .wolf/ memory TTL = 30 days matching raw data retention. Mounted to persistent volume (Azure File Share or Google Drive).
── Phase 4b: OpenClaw — Containerised Orchestration + MIDAS Skill Library
OC-1 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Containerise OpenClaw gateway — Docker image with env vars, no plaintext credentials | High | OPEN | 3 | wave-8,openclaw,new | BLOCKED BY: CRON-2. AC: docker run -p 18789:18789 andreaskasper/openclaw. All credentials via env vars. No secrets in image or config files.
OC-2 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Build MIDAS skill library v1.0 — get_regime_state, get_sec_signal, enforce_risk_policy | High | OPEN | 5 | wave-8,openclaw,agent-integrated,new | BLOCKED BY: MCP-1. AC: 6 skills deployed: get_regime_state, get_gamma_profile, get_sec_signal, get_insider_activity, enforce_risk_policy, validate_trade_integrity. Each skill queries Gold only — no recomputation.
OC-3 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Wire OpenClaw skills to Gold tables — enforce read-only no-recomputation rule | High | OPEN | 5 | wave-8,openclaw,agent-integrated,new | BLOCKED BY: OC-2, TGRAPH-5. AC: Each skill definition contains constraint: NEVER recompute conviction_cap or regime_label. SELECT only from midas.gold.*. Validated by TGRAPH-7 assertion.
OC-4 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Build get_midas_consensus skill — deterministic fusion of regime + gamma + SEC signals | Med | OPEN | 3 | wave-8,openclaw,new | BLOCKED BY: OC-3. AC: Skill returns signal (HIGH_CONFIDENCE_SHORT/FADE_LONG/NEUTRAL), conviction (0-1), drivers list. Logic: deterministic CASE mapping — no LLM reasoning.
OC-5 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Build execute_trade_policy skill — conviction gate + risk cap enforcement | Med | OPEN | 3 | wave-8,openclaw,new | BLOCKED BY: OC-4, GOLD-2. AC: If regime=BLOCKED OR conviction<0.6 → blocked=True. All trade attempts logged to midas.gold.trade_log. No execution without policy pass.
OC-6 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Wire OpenClaw to TrustGraph MCP for causal chain retrieval during skill execution | Med | OPEN | 2 | wave-8,openclaw,trustgraph,new | BLOCKED BY: TGRAPH-5, OC-3. AC: Before trade execution, skill calls TrustGraph to retrieve causal path: [regime]→[rule]→[conviction_cap]. Logged as explanation.
── Phase 4c: LMCache — Inference Caching (LOW priority — benchmark first)
LMC-1 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Evaluate LMCache deployment — benchmark KV reuse for Phase 0-5 NEWS_CORPUS sessions | Low | OPEN | 3 | wave-8,lmcache,new | BLOCKED BY: OC-1. AC: Benchmark report comparing token cost with/without LMCache for 5 Phase 0-5 runs. Only proceed to LMC-2 if token reduction >30% or cost >$0.50/day.
LMC-2 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Configure LMCache vLLM endpoint — docker pull lmcache/vllm-openai, wire to OpenClaw | Low | OPEN | 3 | wave-8,lmcache,new | BLOCKED BY: LMC-1 benchmark PASS. AC: OpenClaw points to lmcache endpoint. KV reuse confirmed in LMCache dashboard. Token usage reduction measurable in OpenWolf ledger.
── Phase 4d: Network — Tailscale Private Mesh
NET-1 | Story | MIDAS-200 | Agentic Infra Stack | WAVE 8 | Team 0: SE-Infra | Provision Tailscale mesh — local node + Databricks + TrustGraph + OpenClaw VM | Med | OPEN | 2 | wave-8,infrastructure,new | AC: All nodes on Tailscale network. No public ports. Colab test environment can reach local TrustGraph via Tailscale. OpenClaw VM can reach Databricks via Tailscale. Net-1 enables hybrid local+cloud topology.
Wave 8 Total: 20 stories ¦ 64 story points ¦ Owner: Team 0: SE-Infra ¦ All stories NEW (★) ¦ Gate: GOLD-1 before Phase 3, CRON-2 before Phase 4